## Detail Task
Sprint | Tim | Issue # | Task | Mahasiswa | SP | Status | Tanggal Selesai | Deadline | Status Waktu | Hari Terlambat | Link Issue | Catatan
Sprint 1 | Tim 01 | #4 | task: prd drafting | Arini Nur Azizah | 5 | Done | 2026-09-13 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPSTONE-01/issues/4 | https://docs.google.com/document/d/178KRQQkjTAaoMe2GDTmoy3uSA2fxjGrg96jCD7PCdqg/edit?usp=sharing
Sprint 1 | Tim 01 | #1 | task: folder structure | Rafie Zaidan Umara | 3 | Done | 2026-09-21 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPSTONE-01/issues/1
Sprint 1 | Tim 01 | #2 | task: frontend template | Zabrina Zerlynda Musanef | 8 | Done | 2026-09-25 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPSTONE-01/issues/2
Sprint 1 | Tim 01 | #3 | task: backend template | Muhammad Rengga Putra Kuncoro | 8 | Done | 2026-09-25 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPSTONE-01/issues/3
Sprint 1 | Tim 01 | #5 | task: prd finalization | Arini Nur Azizah | 5 | Done | 2026-09-21 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPSTONE-01/issues/5 | https://docs.google.com/document/d/1J6m3jH4bDKTOxLXlXFbdRxoYl5YmiYyX/edit?usp=drive_link&ouid=105136930215355298933&rtpof=true&sd=true
Sprint 1 | Tim 01 | #6 | task: exploratory data analysis | Mufrih Fakhir | 5 | Blocked | - | 2026-09-26 | Terlambat | 4 | https://github.com/if-capstone-26/CAPSTONE-01/issues/6 | still waiting on data
Sprint 2 | Tim 01 | #19 | chore: create db schema and integrate postgres | Muhammad Rengga Putra Kuncoro | 5 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-01/issues/19
Sprint 2 | Tim 01 | #18 | chore: run app with docker compose up | Rafie Zaidan Umara | 5 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-01/issues/18
Sprint 2 | Tim 01 | #15 | fix: frontend recommendation system | Zabrina Zerlynda Musanef | 3 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-01/issues/15
Sprint 2 | Tim 01 | #16 | feat: wire recommendation system | Muhammad Rengga Putra Kuncoro | 5 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-01/issues/16
Sprint 2 | Tim 01 | (Draft) | task: ews threshold & rkap mapping | Arini Nur Azizah | 5 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 01 | (Draft) | task: rbac matrix & permission spec | Arini Nur Azizah | 5 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 01 | (Draft) | task: data pre-processing | Mufrih Fakhir | 8 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 01 | (Draft) | feat: single uko dashboard layout | Zabrina Zerlynda Musanef | 8 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 01 | (Draft) | feat: ews calculation engine | Muhammad Rengga Putra Kuncoro | 8 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 01 | (Draft) | feat: rbac middleware uko level | Muhammad Rengga Putra Kuncoro | 5 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 01 | (Draft) | test: ews threshold automated test | Rafie Zaidan Umara | 5 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 01 | (Draft) | feat: ews alert widget frontend | Zabrina Zerlynda Musanef | 5 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 01 | (Draft) | task: setup staging deployment | Rafie Zaidan Umara | 5 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 01 | (Draft) | task: cluster criteria & anomaly rule specification | Arini Nur Azizah | 5 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 01 | (Draft) | feat: anomaly clustering ai model | Mufrih Fakhir | 13 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 01 | (Draft) | feat: anomaly grouping service | Muhammad Rengga Putra Kuncoro | 8 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 01 | (Draft) | test: clustering algorithm validation test | Rafie Zaidan Umara | 5 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 01 | (Draft) | feat: anomaly summary widget frontend | Zabrina Zerlynda Musanef | 8 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 01 | (Draft) | task: vast.ai gpu setup & deployment | Rafie Zaidan Umara | 13 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 01 | (Draft) | task: area head workflow & grid view spec | Arini Nur Azizah | 5 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 01 | (Draft) | task: drill-down read-only acceptance spec | Arini Nur Azizah | 5 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 01 | (Draft) | task: rkap document embedding & vector store indexing | Mufrih Fakhir | 8 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 01 | (Draft) | feat: area grid view dashboard | Zabrina Zerlynda Musanef | 13 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 01 | (Draft) | feat: area level rbac middleware | Muhammad Rengga Putra Kuncoro | 8 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 01 | (Draft) | feat: uko drill-down navigation frontend | Zabrina Zerlynda Musanef | 8 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 01 | (Draft) | test: endpoint load & security test | Rafie Zaidan Umara | 8 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 01 | (Draft) | task: rkap policy knowledge base & catalog mapping | Arini Nur Azizah | 8 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 01 | (Draft) | feat: rkap recommendation rag engine | Mufrih Fakhir | 13 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 01 | (Draft) | feat: ai recommendation integration api | Muhammad Rengga Putra Kuncoro | 8 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 01 | (Draft) | feat: ai recommendation ui panel | Zabrina Zerlynda Musanef | 8 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 01 | (Draft) | test: recommendation alignment integration test | Rafie Zaidan Umara | 5 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 01 | (Draft) | task: llm inference engine deployment | Rafie Zaidan Umara | 13 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 01 | (Draft) | task: executive view requirements & user acceptance test | Arini Nur Azizah | 8 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 01 | (Draft) | feat: regional executive dashboard | Zabrina Zerlynda Musanef | 13 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 01 | (Draft) | feat: reinforcement scoring ai model | Mufrih Fakhir | 13 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 01 | (Draft) | feat: concurrency & data locking engine | Muhammad Rengga Putra Kuncoro | 5 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 01 | (Draft) | test: end-to-end integration & concurrency test | Rafie Zaidan Umara | 8 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 01 | (Draft) | task: final production deployment | Rafie Zaidan Umara | 8 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | -
Sprint 1 | Tim 02 | #1 | PRD drafting | Nona Auliya Wijaya | 3 | Done | 2026-09-24 | 2026-10-09 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/1
Sprint 1 | Tim 02 | #2 | Project Charter Drafting | Leyan Harits Rambang Wicaksana | 3 | Done | 2026-09-24 | 2026-10-09 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/2
Sprint 1 | Tim 02 | #3 | Project Charter & PRD Finalization | Leyan Harits Rambang Wicaksana | 3 | Done | 2026-09-25 | 2026-10-09 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/3
Sprint 1 | Tim 02 | #4 | Setup Repository, CI/CD Pipeline & Staging Environment | Haidar Daffa Firzatullah | 5 | Todo | - | 2026-10-09 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/4
Sprint 1 | Tim 02 | #5 | Perancangan Dynamic State Machine Alur Verifikasi Fleksibel | Leyan Harits Rambang Wicaksana | 5 | Todo | - | 2026-10-09 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/5
Sprint 1 | Tim 02 | #10 | Redesign Wireframe & UI Design System Librigo | Amelia Nova Safitri | 3 | Todo | - | 2026-10-09 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/10
Sprint 1 | Tim 02 | #38 | Review Schema DB & Validation Rule Dynamic State Engine | Belum di-assign | 0 | Todo | - | 2026-10-09 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/38
Sprint 2 | Tim 02 | #6 | Interface Dynamic Stepper & Independent Verification Tabs (Isu 3) | Amelia Nova Safitri | 5 | Todo | - | 2026-10-23 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/6
Sprint 2 | Tim 02 | #8 | Implementation Endpoint API Decoupled Workflow Validasi & Publikasi | Leyan Harits Rambang Wicaksana | 8 | Todo | - | 2026-10-23 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/8
Sprint 2 | Tim 02 | #9 | Matrix Skenario Testing Alur Fleksibel & Audit Eksisting | Nona Auliya Wijaya | 3 | Todo | - | 2026-10-23 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/9
Sprint 2 | Tim 02 | #12 | Verification Middleware & Permission Guard Engine | Akmal Bobsaid | 5 | Todo | - | 2026-10-23 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/12
Sprint 2 | Tim 02 | #13 | Automated Unit Testing Suite for Verification Workflow | Haidar Daffa Firzatullah | 5 | Todo | - | 2026-10-23 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/13
Sprint 3 | Tim 02 | #14 | API Edit Data Mahasiswa Mandiri oleh Staf (Isu 1) | Akmal Bobsaid | 5 | Todo | - | 2026-11-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/14
Sprint 3 | Tim 02 | #15 | Demo Tengah Semester & Berita Acara Review Mitra | Nona Auliya Wijaya, Leyan Harits Rambang Wicaksana | 3 | Todo | - | 2026-11-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/15
Sprint 3 | Tim 02 | #16 | UI Form Edit Data Mahasiswa Mandiri pada Dashboard Staf (Isu 1) | Amelia Nova Safitri | 3 | Todo | - | 2026-11-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/16
Sprint 3 | Tim 02 | #17 | Fix Error Menu Tambah Fakultas & Departemen (Isu 2) | Belum di-assign | 3 | Todo | - | 2026-11-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/17
Sprint 3 | Tim 02 | #18 | Data Migration & Sanity Checking Script for Master Data | Haidar Daffa Firzatullah | 3 | Todo | - | 2026-11-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/18
Sprint 3 | Tim 02 | #37 | UI Integration Link Repository & Eprint ID di Dashboard Mahasiswa (Isu 4) | Amelia Nova Safitri | 3 | Todo | - | 2026-11-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/37
Sprint 4 | Tim 02 | #19 | Logging Engine & Audit Trail Petugas Verifikasi (Isu 5) | Belum di-assign | 8 | Todo | - | 2026-11-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/19
Sprint 4 | Tim 02 | #35 | UI Component Display Identitas Petugas per Tahapan Verifikasi (Isu 5) | Belum di-assign | 3 | Todo | - | 2026-11-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/35
Sprint 4 | Tim 02 | #20 | Sistem Catatan & Histori Revisi Penolakan Multi-Admin (Isu 8) | Belum di-assign | 5 | Todo | - | 2026-11-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/20
Sprint 4 | Tim 02 | #36 | UI Component Histori Catatan Penolakan di Menu Tolak (Isu 8) | Belum di-assign | 3 | Todo | - | 2026-11-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/36
Sprint 4 | Tim 02 | #21 | Kolom Pengisian Link Repository & Eprint ID di Layanan Publikasi (Isu 4) | Belum di-assign | 3 | Todo | - | 2026-11-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/21
Sprint 4 | Tim 02 | #22 | Audit Log Indexing Strategy & Flow Compliance Documentation | Belum di-assign | 3 | Todo | - | 2026-11-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/22
Sprint 5 | Tim 02 | #23 | Generator Nomor Surat Bebas Pustaka Periode Wisuda & Tahun (Isu 7) | Belum di-assign | 5 | Todo | - | 2026-12-04 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/23
Sprint 5 | Tim 02 | #24 | Security Reset Form Search NRP saat Pindah Tahap (Isu 9) | Belum di-assign | 3 | Todo | - | 2026-12-04 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/24
Sprint 5 | Tim 02 | #25 | Feature Sort Berdasarkan Urutan Registrasi pada Tahap Aktivasi (Isu 6) | Leyan Harits Rambang Wicaksana | 2 | Todo | - | 2026-12-04 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/25
Sprint 5 | Tim 02 | #26 | Position Tombol NEXT di Bagian Atas Halaman (Header Navigation) (Isu 10) | Belum di-assign | 2 | Todo | - | 2026-12-04 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/26
Sprint 5 | Tim 02 | #27 | Performance & Load Testing for Data Table Sorting & Search Queries | Belum di-assign | 3 | Todo | - | 2026-12-04 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/27
Sprint 6 | Tim 02 | #28 | Eksekusi User Acceptance Testing (UAT) Bersama Staf Perpustakaan ITS | Belum di-assign | 8 | Todo | - | 2026-12-18 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/28
Sprint 6 | Tim 02 | #29 | End-to-End Automated Testing Suite Execution | Belum di-assign | 5 | Todo | - | 2026-12-18 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/29
Sprint 6 | Tim 02 | #31 | Patching Final Bug Hasil Temuan UAT Mitra | Belum di-assign | 3 | Todo | - | 2026-12-18 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/31
Sprint 7 | Tim 02 | #30 | Penyusunan Dokumen Laporan Akhir Tim & Laporan Konversi | Belum di-assign | 5 | Todo | - | 2027-01-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/30
Sprint 7 | Tim 02 | #32 | Pengumpulan Kuitansi & Laporan Realisasi Penggunaan Dana (RPD) | Nona Auliya Wijaya | 2 | Todo | - | 2027-01-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/32
Sprint 7 | Tim 02 | #33 | Release Handover, Production Deployment & API Docs Finalization | Haidar Daffa Firzatullah | 3 | Todo | - | 2027-01-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/33
Sprint 7 | Tim 02 | #34 | Final Presentation Deck & System Live Demo Preparation for Sidang | Leyan Harits Rambang Wicaksana | 3 | Todo | - | 2027-01-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPSTONE-02_Librigo/issues/34
Sprint 1: Persiapan | Tim 03 | #1 | BE - Buat Skema DBMS | Junathan Richie | 5 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/1
Sprint 1: Persiapan | Tim 03 | #2 | BE - Design API Contract | Junathan Richie | 3 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/2
Sprint 1: Persiapan | Tim 03 | #4 | UI/UX - Design Guest Management Page | Kukuh Putra Purwanegara | 3 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/4
Sprint 1: Persiapan | Tim 03 | #5 | UI/UX - Design Profile Page | Kukuh Putra Purwanegara | 2 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/5
Sprint 1: Persiapan | Tim 03 | #6 | UI/UX - Design Login Page | Andi Nur Nabila Syalwani | 2 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/6
Sprint 1: Persiapan | Tim 03 | #7 | UI/UX - Superadmin Dashboard | Andi Nur Nabila Syalwani | 5 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/7
Sprint 1: Persiapan | Tim 03 | #9 | UI/UX - Dashboard Admin Event | Andi Nur Nabila Syalwani | 5 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/9
Sprint 1: Persiapan | Tim 03 | #10 | PL - Beli dan Setup VPS | Faith Mary Sani | 2 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/10
Sprint 1: Persiapan | Tim 03 | #13 | PL - Setup CI/CD + Docker | Faith Mary Sani | 5 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/13
Sprint 1: Persiapan | Tim 03 | #20 | AN - Create Product Requirements Document Draft | Kukuh Putra Purwanegara | 3 | Done | 2026-09-13 | 2026-09-15 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/20
Sprint 2: Persiapan | Tim 03 | #3 | AN - Fiksasi Product Requirements Document | Kukuh Putra Purwanegara | 2 | Done | 2026-09-21 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/3
Sprint 2: Persiapan | Tim 03 | #11 | BE - Rest API User | Junathan Richie | 3 | Done | 2026-09-19 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/11
Sprint 2: Persiapan | Tim 03 | #12 | FE - Login Page | Andi Nur Nabila Syalwani | 3 | Done | 2026-09-20 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/12
Sprint 2: Persiapan | Tim 03 | #14 | BE - Rest API Auth | Junathan Richie | 3 | Done | 2026-09-19 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/14
Sprint 2: Persiapan | Tim 03 | #15 | BE - Rest API Invitations | Junathan Richie | 5 | Done | 2026-09-20 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/15
Sprint 2: Persiapan | Tim 03 | #16 | PL - Unittest Auth API | Faith Mary Sani | 3 | Done | 2026-09-21 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/16
Sprint 2: Persiapan | Tim 03 | #17 | PL - Unittest User | Faith Mary Sani | 3 | Done | 2026-09-21 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/17
Sprint 2: Persiapan | Tim 03 | #18 | PL - Unittest Invitation API | Faith Mary Sani | 3 | Done | 2026-09-21 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/18
Sprint 2: Persiapan | Tim 03 | #19 | AN - Create Non Disclosure Agreement Draft | Kukuh Putra Purwanegara | 3 | Done | 2026-09-21 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/19
Sprint 3: Login (Integrasi) | Tim 03 | #6 | PL - Setup Deployment FE di VPS | Faith Mary Sani | 2 | Done | 2026-09-28 | 2026-09-29 | Tepat waktu | 0 | https://github.com/if-capstone-26/capstone-03/issues/6
Sprint 3: Login (Integrasi) | Tim 03 | #2 | FE - Integrasi Login | Kukuh Putra Purwanegara | 3 | Done | 2026-09-27 | 2026-09-29 | Tepat waktu | 0 | https://github.com/if-capstone-26/capstone-03/issues/2
Sprint 3: Login (Integrasi) | Tim 03 | #4 | PL - Setup CI/CD di Repo FE | Faith Mary Sani | 3 | Done | 2026-09-28 | 2026-09-29 | Tepat waktu | 0 | https://github.com/if-capstone-26/capstone-03/issues/4
Sprint 3: Login (Integrasi) | Tim 03 | #3 | BE - API Invitation Member | Junathan Richie | 3 | Done | 2026-09-26 | 2026-09-29 | Tepat waktu | 0 | https://github.com/if-capstone-26/capstone-03/issues/3
Sprint 3: Login (Integrasi) | Tim 03 | #1 | FE - Kelola Akun Admin: Halaman Lihat & Hapus: Slicing | Andi Nur Nabila Syalwani | 3 | Done | 2026-09-26 | 2026-09-29 | Tepat waktu | 0 | https://github.com/if-capstone-26/capstone-03/issues/1
Sprint 3: Login (Integrasi) | Tim 03 | #5 | FE - Kelola Akun Admin: Halaman Tambah Admin: Slicing | Kukuh Putra Purwanegara | 3 | Done | 2026-09-28 | 2026-09-29 | Tepat waktu | 0 | https://github.com/if-capstone-26/capstone-03/issues/5
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | BE - Rest API Guests | Junathan Richie | 5 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | BE - API Public Guest QR & QR Code Image | Junathan Richie | 8 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | FE - Kelola Akun Admin: Halaman Lihat & Hapus: Integrasi | Kukuh Putra Purwanegara | 5 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | FE - Kelola Akun Admin: Halaman Tambah Admin: Integrasi | Kukuh Putra Purwanegara | 5 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | FE - Daftar Tamu: Halaman List Tamu (+ modal Tambah Satuan & QR Code): Slicing | Andi Nur Nabila Syalwani | 5 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | FE - Superadmin: Halaman Buat Event: Slicing | Andi Nur Nabila Syalwani | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | FE - Superadmin: Halaman Daftar & Kelola Event: Slicing | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | FE - Superadmin: Halaman Edit Detail Event: Slicing | Andi Nur Nabila Syalwani | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | FE - Superadmin: Halaman Info Detail Event: Slicing | Andi Nur Nabila Syalwani | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | PL - Pengujian Fungsional & Hak Akses CRUD Admin Event | Faith Mary Sani | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 4: Kelola Admin Event | Tim 03 | (Draft) | PL - Setup Integrasi Domain & SSL (dari Mitra) | Faith Mary Sani | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | -
Sprint 5: Kelola Event & Input Data Tamu (Generate QR) | Tim 03 | (Draft) | FE - Daftar Tamu: Halaman List Tamu (+ modal Tambah Satuan & QR Code): Integrasi | Andi Nur Nabila Syalwani | 8 | Todo | - | 2026-10-13 | Belum jatuh tempo | 0 | -
Sprint 5: Kelola Event & Input Data Tamu (Generate QR) | Tim 03 | (Draft) | FE - Superadmin: Halaman Buat Event: Integrasi | Andi Nur Nabila Syalwani | 5 | Todo | - | 2026-10-13 | Belum jatuh tempo | 0 | -
Sprint 5: Kelola Event & Input Data Tamu (Generate QR) | Tim 03 | (Draft) | FE - Superadmin: Halaman Daftar & Kelola Event: Integrasi | Andi Nur Nabila Syalwani | 5 | Todo | - | 2026-10-13 | Belum jatuh tempo | 0 | -
Sprint 5: Kelola Event & Input Data Tamu (Generate QR) | Tim 03 | (Draft) | FE - Superadmin: Halaman Edit Detail Event: Integrasi | Kukuh Putra Purwanegara | 5 | Todo | - | 2026-10-13 | Belum jatuh tempo | 0 | -
Sprint 5: Kelola Event & Input Data Tamu (Generate QR) | Tim 03 | (Draft) | FE - Superadmin: Halaman Info Detail Event: Integrasi | Junathan Richie | 5 | Todo | - | 2026-10-13 | Belum jatuh tempo | 0 | -
Sprint 5: Kelola Event & Input Data Tamu (Generate QR) | Tim 03 | (Draft) | FE - Daftar Tamu: Halaman Edit Tamu: Slicing | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-10-13 | Belum jatuh tempo | 0 | -
Sprint 5: Kelola Event & Input Data Tamu (Generate QR) | Tim 03 | (Draft) | PL - Pengujian Generator QR Code & Integritas Data Tamu | Faith Mary Sani | 3 | Todo | - | 2026-10-13 | Belum jatuh tempo | 0 | -
Sprint 6: CRUD Tamu pada Event yang Di-assign | Tim 03 | (Draft) | BE - API Check-in (Scan QR) | Junathan Richie | 8 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 6: CRUD Tamu pada Event yang Di-assign | Tim 03 | (Draft) | PL - Unittest Guests & Check-in API | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 6: CRUD Tamu pada Event yang Di-assign | Tim 03 | (Draft) | FE - Daftar Tamu: Halaman Edit Tamu: Integrasi | Andi Nur Nabila Syalwani | 5 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 6: CRUD Tamu pada Event yang Di-assign | Tim 03 | (Draft) | PL - Setup Monitoring Server (Sebelum Load Testing) | Faith Mary Sani | 5 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 7: Scanner QR | Tim 03 | (Draft) | PL - Load Testing API Scanner | Faith Mary Sani | 5 | Todo | - | 2026-10-27 | Belum jatuh tempo | 0 | -
Sprint 7: Scanner QR | Tim 03 | (Draft) | BE - API Dashboard & Export Laporan Kehadiran | Junathan Richie | 8 | Todo | - | 2026-10-27 | Belum jatuh tempo | 0 | -
Sprint 7: Scanner QR | Tim 03 | (Draft) | FE - Admin Event Dashboard (Scanner + Buku Tamu + Statistik + Export): Slicing | Andi Nur Nabila Syalwani | 8 | Todo | - | 2026-10-27 | Belum jatuh tempo | 0 | -
Sprint 7: Scanner QR | Tim 03 | (Draft) | PL - E2E Testing: Alur Scan QR (Otomatis) | Kukuh Putra Purwanegara | 5 | Todo | - | 2026-10-27 | Belum jatuh tempo | 0 | -
Sprint 8: Status Kehadiran, Check-in Manual & Export PDF | Tim 03 | (Draft) | PL - Pengujian Dashboard & Export PDF | Faith Mary Sani | 5 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 8: Status Kehadiran, Check-in Manual & Export PDF | Tim 03 | (Draft) | BE - API Kelola Event untuk Admin Event | Junathan Richie | 5 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 8: Status Kehadiran, Check-in Manual & Export PDF | Tim 03 | (Draft) | FE - Admin Event Dashboard (Scanner + Buku Tamu + Statistik + Export): Integrasi | Andi Nur Nabila Syalwani | 8 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 8: Status Kehadiran, Check-in Manual & Export PDF | Tim 03 | (Draft) | FE - Admin Event: Halaman Detail Event (View): Slicing | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 8: Status Kehadiran, Check-in Manual & Export PDF | Tim 03 | (Draft) | PL - E2E Testing: Alur Check-in Manual & Dashboard Kehadiran | Faith Mary Sani | 5 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 8: Status Kehadiran, Check-in Manual & Export PDF | Tim 03 | (Draft) | FE - Admin Event: Halaman Edit Event: Slicing | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 9: Kelola Event yang Di-assign (Admin Event) | Tim 03 | (Draft) | BE - API Dashboard Superadmin | Junathan Richie | 8 | Todo | - | 2026-11-10 | Belum jatuh tempo | 0 | -
Sprint 9: Kelola Event yang Di-assign (Admin Event) | Tim 03 | (Draft) | FE - Admin Event: Halaman Detail Event (View): Integrasi | Andi Nur Nabila Syalwani | 5 | Todo | - | 2026-11-10 | Belum jatuh tempo | 0 | -
Sprint 9: Kelola Event yang Di-assign (Admin Event) | Tim 03 | (Draft) | FE - Superadmin Dashboard: Statistik Global: Slicing | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-11-10 | Belum jatuh tempo | 0 | -
Sprint 9: Kelola Event yang Di-assign (Admin Event) | Tim 03 | (Draft) | PL - Unittest Access Control (Admin Event A vs B) | Faith Mary Sani | 3 | Todo | - | 2026-11-10 | Belum jatuh tempo | 0 | -
Sprint 9: Kelola Event yang Di-assign (Admin Event) | Tim 03 | (Draft) | FE - Admin Event: Halaman Edit Event: Integrasi | Andi Nur Nabila Syalwani | 5 | Todo | - | 2026-11-10 | Belum jatuh tempo | 0 | -
Sprint 9: Kelola Event yang Di-assign (Admin Event) | Tim 03 | (Draft) | PL - Setup Database Backup & Restore Drill | Faith Mary Sani | 3 | Todo | - | 2026-11-10 | Belum jatuh tempo | 0 | -
Sprint 10: Dashboard Superadmin | Tim 03 | (Draft) | BE - API Update Profile & Password | Junathan Richie | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 10: Dashboard Superadmin | Tim 03 | (Draft) | FE - Superadmin Dashboard: Statistik Global: Integrasi | Andi Nur Nabila Syalwani | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 10: Dashboard Superadmin | Tim 03 | (Draft) | FE - Halaman Profile: Slicing | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 10: Dashboard Superadmin | Tim 03 | (Draft) | FE - Halaman Ubah Password: Slicing | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 10: Dashboard Superadmin | Tim 03 | (Draft) | PL - Load Testing API Dashboard Superadmin | Faith Mary Sani | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 11: Modifikasi Profile | Tim 03 | (Draft) | PL - Pengujian Keamanan Ganti Password | Faith Mary Sani | 3 | Todo | - | 2026-11-24 | Belum jatuh tempo | 0 | -
Sprint 11: Modifikasi Profile | Tim 03 | (Draft) | FE - Halaman Profile: Integrasi | Andi Nur Nabila Syalwani | 5 | Todo | - | 2026-11-24 | Belum jatuh tempo | 0 | -
Sprint 11: Modifikasi Profile | Tim 03 | (Draft) | FE - Halaman Ubah Password: Integrasi | Junathan Richie | 5 | Todo | - | 2026-11-24 | Belum jatuh tempo | 0 | -
Sprint 11: Modifikasi Profile | Tim 03 | (Draft) | PL - E2E Testing: Alur Superadmin (Kelola Event, Akun Admin, Dashboard, Profile) | Kukuh Putra Purwanegara | 5 | Todo | - | 2026-11-24 | Belum jatuh tempo | 0 | -
Sprint 11: Modifikasi Profile | Tim 03 | (Draft) | PL - Setup Health-check Endpoint & Alerting Otomatis | Faith Mary Sani | 5 | Todo | - | 2026-11-24 | Belum jatuh tempo | 0 | -
Sprint 12: Pengujian & Revisi (UAT) | Tim 03 | (Draft) | AN - User Acceptance Testing (UAT) | Kukuh Putra Purwanegara | 5 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 12: Pengujian & Revisi (UAT) | Tim 03 | (Draft) | BE - Dukungan Teknis & Standby Bug Fix Selama UAT | Junathan Richie | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 12: Pengujian & Revisi (UAT) | Tim 03 | (Draft) | FE - Dukungan Teknis & Standby Bug Fix Selama UAT | Andi Nur Nabila Syalwani | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 12: Pengujian & Revisi (UAT) | Tim 03 | (Draft) | PL - Monitoring Infrastruktur Selama Sesi UAT | Faith Mary Sani | 2 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 13: Pengujian & Revisi (Bugfix & E2E Final) | Tim 03 | (Draft) | PL - End-to-End (E2E) Testing & Pengujian Infrastruktur Akhir | Faith Mary Sani | 5 | Todo | - | 2026-12-08 | Belum jatuh tempo | 0 | -
Sprint 13: Pengujian & Revisi (Bugfix & E2E Final) | Tim 03 | (Draft) | BE - Bug Fixing & Optimasi Backend Pasca UAT | Junathan Richie | 5 | Todo | - | 2026-12-08 | Belum jatuh tempo | 0 | -
Sprint 13: Pengujian & Revisi (Bugfix & E2E Final) | Tim 03 | (Draft) | FE - Bug Fixing & Optimasi Frontend Pasca UAT | Andi Nur Nabila Syalwani | 5 | Todo | - | 2026-12-08 | Belum jatuh tempo | 0 | -
Sprint 13: Pengujian & Revisi (Bugfix & E2E Final) | Tim 03 | (Draft) | AN - Draft Laporan Akhir | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-12-08 | Belum jatuh tempo | 0 | -
Sprint 14: Laporan Akhir | Tim 03 | (Draft) | AN - Laporan Akhir & User Manual | Kukuh Putra Purwanegara | 5 | Todo | - | 2026-12-15 | Belum jatuh tempo | 0 | -
Sprint 14: Laporan Akhir | Tim 03 | (Draft) | BE - Rapikan Repository & Dokumentasi API | Junathan Richie | 3 | Todo | - | 2026-12-15 | Belum jatuh tempo | 0 | -
Sprint 14: Laporan Akhir | Tim 03 | (Draft) | FE - Rapikan Repository & Dokumentasi Deployment FE | Andi Nur Nabila Syalwani | 3 | Todo | - | 2026-12-15 | Belum jatuh tempo | 0 | -
Sprint 14: Laporan Akhir | Tim 03 | (Draft) | PL - Dokumentasi Infrastruktur & Instruksi Deployment | Faith Mary Sani | 3 | Todo | - | 2026-12-15 | Belum jatuh tempo | 0 | -
Sprint 15: Laporan Akhir & Handover | Tim 03 | (Draft) | PL - Handover Akses Sistem ke Mitra | Faith Mary Sani | 5 | Todo | - | 2026-12-22 | Belum jatuh tempo | 0 | -
Sprint 15: Laporan Akhir & Handover | Tim 03 | (Draft) | AN - Dokumen Serah Terima Proyek | Kukuh Putra Purwanegara | 3 | Todo | - | 2026-12-22 | Belum jatuh tempo | 0 | -
Sprint 15: Laporan Akhir & Handover | Tim 03 | (Draft) | BE - Final Review dan Pelatihan Maintenance Repository BE | Junathan Richie | 2 | Todo | - | 2026-12-22 | Belum jatuh tempo | 0 | -
Sprint 15: Laporan Akhir & Handover | Tim 03 | (Draft) | FE - Final Review dan Pelatihan Maintenance Repository FE | Andi Nur Nabila Syalwani | 2 | Todo | - | 2026-12-22 | Belum jatuh tempo | 0 | -
Sprint 1 | Tim 04 | #2 | Gather Requirements, Setup Github Project, Define Scope, etc | Nixon Castroman | 5 | Done | 2026-09-21 | 2026-10-06 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPS04---BJTM/issues/2
Sprint 1 | Tim 04 | #3 | Build BE rough collector | Bunga Melati Putri Luqman | 3 | In progress | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPS04---BJTM/issues/3
Sprint 1 | Tim 04 | #8 | User flow prototype (dashboard) | Nicholas Abel Nathaniel | 3 | Done | 2026-09-25 | 2026-10-06 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPS04---BJTM/issues/8
Sprint 1 | Tim 04 | #1 | Setup Docker environment (isolated sandbox) | Bunga Melati Putri Luqman | 5 | Done | 2026-09-25 | 2026-10-06 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPS04---BJTM/issues/1
Sprint 1 | Tim 04 | #7 | Build enrichment + risk scoring prototype | Haenu Narendra Ramadhani | 5 | Done | 2026-09-25 | 2026-10-06 | Tepat waktu | 0 | https://github.com/if-capstone-26/CAPS04---BJTM/issues/7
Sprint 1 | Tim 04 | #9 | Sprint review 1 | Nixon Castroman | 1 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPS04---BJTM/issues/9
Sprint 1 | Tim 04 | #10 | Align DA prototype with BE finding format | Haenu Narendra Ramadhani | 2 | In progress | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/CAPS04---BJTM/issues/10
Sprint 2 | Tim 04 | (Draft) | Build subdomain discovery from seed domain | Bunga Melati Putri Luqman | 5 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 04 | (Draft) | Build asset/indicator inventory + configurable brand keywords | Bunga Melati Putri Luqman | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 04 | (Draft) | Build normalization & deduplication v1 | Haenu Narendra Ramadhani | 5 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 04 | (Draft) | Build dashboard skeleton with mock data | Nicholas Abel Nathaniel | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 04 | (Draft) | Setup CI pipeline (GitHub Actions) | Daniel Yunus Yumame | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 04 | (Draft) | Sprint review 2 | Nixon Castroman | 1 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 04 | (Draft) | Build collector framework (scheduler + logging) | Bunga Melati Putri Luqman | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 04 | (Draft) | Build connectors: paste site & Tor index (Ahmia) | Bunga Melati Putri Luqman | 5 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 04 | (Draft) | Build phishing domain detection (typosquat) | Haenu Narendra Ramadhani | 5 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 04 | (Draft) | Build findings API endpoints (FastAPI) | Bunga Melati Putri Luqman | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 04 | (Draft) | Connect dashboard to API + filters | Nicholas Abel Nathaniel | 5 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 04 | (Draft) | Implement mandatory controls (rate limit, audit log, allowlist) | Daniel Yunus Yumame | 5 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 04 | (Draft) | Sprint review 3 | Nixon Castroman | 1 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 04 | (Draft) | Integrate enrichment module into pipeline | Bunga Melati Putri Luqman | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 04 | (Draft) | Build risk scoring engine | Haenu Narendra Ramadhani | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 04 | (Draft) | Build alert & notification module | Bunga Melati Putri Luqman | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 04 | (Draft) | Build evidence record & alert views | Nicholas Abel Nathaniel | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 04 | (Draft) | End-to-end integration test (seed → dashboard) | Daniel Yunus Yumame | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 04 | (Draft) | Sprint review 4 (end-to-end demo) | Nixon Castroman | 2 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 04 | (Draft) | Build connectors: public forum & social media | Bunga Melati Putri Luqman | 5 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 04 | (Draft) | Build threat trend summary (risk management) | Nicholas Abel Nathaniel | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 04 | (Draft) | False-positive tuning round 1 | Haenu Narendra Ramadhani | 5 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 04 | (Draft) | Regression test + compliance audit | Daniel Yunus Yumame | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 04 | (Draft) | UAT plan + UAT round 1 with partner | Nixon Castroman | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 04 | (Draft) | Fix UAT defects (backend) | Bunga Melati Putri Luqman | 3 | Todo | - | 2026-12-15 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 04 | (Draft) | Fix UAT defects + UI polish (frontend) | Nicholas Abel Nathaniel | 3 | Todo | - | 2026-12-15 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 04 | (Draft) | False-positive tuning round 2 + detection metrics | Haenu Narendra Ramadhani | 5 | Todo | - | 2026-12-15 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 04 | (Draft) | Finalize deployment + final regression | Daniel Yunus Yumame | 3 | Todo | - | 2026-12-15 | Belum jatuh tempo | 0 | -
Sprint 6 | Tim 04 | (Draft) | UAT round 2 + Sprint review 6 | Nixon Castroman | 2 | Todo | - | 2026-12-15 | Belum jatuh tempo | 0 | -
Sprint 7 | Tim 04 | (Draft) | Final report, handover & SOC/SIEM integration recommendation | Nixon Castroman | 5 | Todo | - | 2026-12-29 | Belum jatuh tempo | 0 | -
Sprint 7 | Tim 04 | (Draft) | API & backend technical documentation | Bunga Melati Putri Luqman | 2 | Todo | - | 2026-12-29 | Belum jatuh tempo | 0 | -
Sprint 7 | Tim 04 | (Draft) | Dashboard user guide | Nicholas Abel Nathaniel | 2 | Todo | - | 2026-12-29 | Belum jatuh tempo | 0 | -
Sprint 7 | Tim 04 | (Draft) | Detection evaluation report | Haenu Narendra Ramadhani | 2 | Todo | - | 2026-12-29 | Belum jatuh tempo | 0 | -
Sprint 7 | Tim 04 | (Draft) | Deployment & operator guide | Daniel Yunus Yumame | 2 | Todo | - | 2026-12-29 | Belum jatuh tempo | 0 | -
Sprint 1 | Tim 05 | #23 | [F0-S1] AI-T10 · Siapkan format laporan rapat mingguan | Ahmad Zaky Ash Shidqi | 2 | Done | 2026-09-22 | 2026-09-14 | Terlambat | 8 | https://github.com/hero-ojk-its/hero/issues/23 | Carry-over Fase 0 — format dipakai sejak Weekly #2.
Sprint 1 | Tim 05 | #25 | [F0] MITRA OI-04 · Penandatanganan NDA seluruh anggota tim | Ahmad Zaky Ash Shidqi | 0 | Done | 2026-09-22 | 2026-09-14 | Terlambat | 8 | https://github.com/hero-ojk-its/hero/issues/25 | NDA lengkap 5 orang — MoM #2, 15 Sep.
Sprint 1 | Tim 05 | #46 | [F0-S1] Dokumen requirement & arsitektur HERO | Ahmad Zaky Ash Shidqi | 0 | Done | 2026-09-09 | 2026-09-14 | Tepat waktu | 0 | https://github.com/hero-ojk-its/hero/issues/46
Sprint 2 | Tim 05 | #2 | [F1-S2] US-12 · Kelola daftar situs sumber | Moh. Rafli Gusti Saputra | 5 | In progress | - | 2026-09-28 | Terlambat | 2 | https://github.com/hero-ojk-its/hero/issues/2 | Dilaporkan selesai (CRUD) di Weekly #3, 22 Sep — tunggu review & staging (DoD).
Sprint 2 | Tim 05 | #3 | [F1-S2] US-13 · Mesin scraping dan pengunduhan PDF | Mirza Syahrizal Fathir | 8 | Done | 2026-09-22 | 2026-09-28 | Tepat waktu | 0 | https://github.com/hero-ojk-its/hero/issues/3 | Baseline scraper selesai (kedalaman 1). Screening sebelum unduh dilanjutkan di #9.
Sprint 2 | Tim 05 | #4 | [F1-S2] US-13a · Kontrol kedalaman crawling per sumber | Mirza Syahrizal Fathir | 5 | Done | - | 2026-09-28 | - | 0 | https://github.com/hero-ojk-its/hero/issues/4 | Kedalaman 1 dulu sampai stabil (arahan mitra). PIC Fathir belum masuk org GitHub.
Sprint 2 | Tim 05 | #5 | [F1-S2] US-14 · Ringkasan hasil job scraping | Moh. Rafli Gusti Saputra | 3 | In progress | - | 2026-09-28 | Terlambat | 2 | https://github.com/hero-ojk-its/hero/issues/5 | Dilaporkan selesai di Weekly #3: berhasil / duplikat / gagal. Progress bar ikut alur scan di #44.
Sprint 2 | Tim 05 | #6 | [F1-S2] US-15 · Unggah dokumen manual | Moh. Rafli Gusti Saputra | 5 | In progress | - | 2026-09-28 | Terlambat | 2 | https://github.com/hero-ojk-its/hero/issues/6 | Selesai (satu & banyak berkas) — Weekly #3. UI dipindah ke bawah Analisa/Draft Tanggapan.
Sprint 2 | Tim 05 | #7 | [F1-S2] US-15a · Pilih tipe dokumen saat unggah: draft kajian atau peraturan eksisting | Moh. Rafli Gusti Saputra | 3 | In progress | - | 2026-09-28 | Terlambat | 2 | https://github.com/hero-ojk-its/hero/issues/7 | Dilaporkan selesai di Weekly #3 — tunggu review & staging (DoD).
Sprint 2 | Tim 05 | #8 | [F1-S2] US-18 · Tolak berkas non-PDF | Moh. Rafli Gusti Saputra | 3 | In progress | - | 2026-09-28 | Terlambat | 2 | https://github.com/hero-ojk-its/hero/issues/8 | Selesai beserta alasan penolakan — Weekly #3. Tunggu review & staging.
Sprint 2 | Tim 05 | #9 | [F1-S2] US-19 · Deteksi duplikat lewat hash dan ukuran berkas | Moh. Rafli Gusti Saputra | 5 | In progress | - | 2026-09-28 | Terlambat | 2 | https://github.com/hero-ojk-its/hero/issues/9 | Cek dulu baru unduh — Weekly #3. Alur scan → centang → pilih tujuan dilanjutkan di #44.
Sprint 2 | Tim 05 | #10 | [F1-S2] US-26 · Simpan dokumen beserta metadata dan teks | Moh. Rafli Gusti Saputra | 5 | In progress | - | 2026-09-28 | Terlambat | 2 | https://github.com/hero-ojk-its/hero/issues/10 | Metadata + teks selesai (Weekly #3). Belum ada penamaan baku sebelum simpan — lihat #12.
Sprint 2 | Tim 05 | #21 | [F1-S2] AI-T3 · Mockup Figma Fase 1 — 9 layar | Muhammad Ikhwan Ma'ruf Santoso | 5 | Done | 2026-09-22 | 2026-09-28 | Tepat waktu | 0 | https://github.com/hero-ojk-its/hero/issues/21 | Figma 4 layar per 15 Sep; link dibagikan 21 Sep, feedback mitra 22 Sep.
Sprint 2 | Tim 05 | #22 | [F1-S2] AI-T7 · Siapkan hosting untuk uji coba mitra 8 Oktober | Hamdancml | 8 | Done | 2026-09-22 | 2026-09-28 | Tepat waktu | 0 | https://github.com/hero-ojk-its/hero/issues/22 | Frontend di-deploy ke Vercel lewat workflow repo. Backend/DB/OCR tetap butuh server — ADR-11.
Sprint 2 | Tim 05 | #24 | [F1] MITRA AI-M1 · Alamat situs sumber ketiga untuk scraping | Ahmad Zaky Ash Shidqi | 0 | Done | - | 2026-09-28 | - | 0 | https://github.com/hero-ojk-its/hero/issues/24 | MITRA — Weekly #3: Pak Faris janji kirim tiga alamat URL. Masih ditunggu — memblokir indikator ≥ 3 situs (M1).
Sprint 2 | Tim 05 | #38 | [F0-S2] F0-3 · Struktur folder knowledge base awal (skeleton) | Moh. Rafli Gusti Saputra | 3 | In progress | - | 2026-09-28 | Terlambat | 2 | https://github.com/hero-ojk-its/hero/issues/38 | Carry-over Fase 0. Usulan struktur: Source → Sektor → Jenis → Tahun → Status (MoM #2).
Sprint 2 | Tim 05 | #43 | [F1-S2] AI-T11 · Revisi mockup Figma sesuai feedback Weekly #3 | Muhammad Ikhwan Ma'ruf Santoso | 0 | Done | 2026-09-28 | 2026-09-28 | Tepat waktu | 0 | https://github.com/hero-ojk-its/hero/issues/43 | Link Figma revisi paling lambat rapat 29 Sep.
Sprint 2 | Tim 05 | #45 | [F1-S2] PRD v1.0 · Review dan tanda tangan Pak Andika | Ahmad Zaky Ash Shidqi | 0 | In progress | - | 2026-09-28 | Terlambat | 2 | https://github.com/hero-ojk-its/hero/issues/45 | Target tanda tangan pekan ini (Weekly #3).
Sprint 3 | Tim 05 | #11 | [F1-S3] US-20 · Ekstraksi metadata dasar | Mirza Syahrizal Fathir | 8 | In progress | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/11
Sprint 3 | Tim 05 | #12 | [F1-S3] US-20a · OCR halaman pertama dan penamaan berkas baku | Mirza Syahrizal Fathir | 5 | In progress | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/12 | Format baku (Weekly #3): nomor peraturan␣nama␣tahun; wildcard bila tak bisa ditentukan. Rename setelah dedup, sebelum simpan.
Sprint 3 | Tim 05 | #13 | [F1-S3] US-21 · Koreksi metadata manual | Muhammad Ikhwan Ma'ruf Santoso | 3 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/13
Sprint 3 | Tim 05 | #14 | [F1-S3] US-23 · Antrian dokumen gagal dan proses ulang | Moh. Rafli Gusti Saputra | 3 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/14
Sprint 3 | Tim 05 | #15 | [F1-S3] US-16 · Baca dokumen dari folder lokal | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/15 | Belum dimulai per Weekly #3. Folder internal ± 500 dok = sumber utama KB.
Sprint 3 | Tim 05 | #16 | [F1-S3] US-24 · Klasifikasi kategori peraturan | Mirza Syahrizal Fathir | 5 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/16 | Hierarki per jenis (UU, PP, POJK, SE) — arahan Pak Faris (MoM #2).
Sprint 3 | Tim 05 | #17 | [F1-S3] US-25 · Penempatan folder: gunakan eksisting atau buat baru | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/17
Sprint 3 | Tim 05 | #18 | [F1-S3] US-27 · Pencarian dokumen | Moh. Rafli Gusti Saputra | 5 | In progress | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/18 | Filter nomor/kategori/tanggal/status sudah; kata kunci bebas berjalan. Frasa multi-kata ("sepatu roda") harus satu frasa.
Sprint 3 | Tim 05 | #19 | [F1-S3] US-28 · Detail dokumen | Muhammad Ikhwan Ma'ruf Santoso | 3 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/19 | Fase 1: teks mentah saja, belum struktur pasal (dok. 06 §5B.4 opsi B).
Sprint 3 | Tim 05 | #20 | [F1-S3] SPIKE US-32a · Purwarupa parser struktur pasal atas 20 dokumen nyata | Belum di-assign | 5 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/20 | Uji asumsi penomoran pasal pada 20 dokumen nyata — menopang summary, harmonisasi, tanggapan.
Sprint 3 | Tim 05 | #26 | [F2] MITRA AI-M2 · Folder OneDrive berisi peraturan internal DPEA | Belum di-assign | 0 | Done | 2026-09-26 | 2026-10-12 | Tepat waktu | 0 | https://github.com/hero-ojk-its/hero/issues/26 | Folder OneDrive sudah tersedia — Fathir mulai retrieval (Weekly #3).
Sprint 3 | Tim 05 | #27 | [F4] MITRA AI-M3..M6 · Contoh surat tanggapan tertulis beserta dokumen dasarnya | Ahmad Zaky Ash Shidqi | 0 | Blocked | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/27 | MITRA — Weekly #3: Pak Faris akan taruh contoh template di folder baru. Tenggat 11 Okt — tagih 29 Sep.
Sprint 3 | Tim 05 | #42 | [F1-S3] SPIKE · Komparasi waktu proses penyimpanan folder PDF vs vektor | Mirza Syahrizal Fathir | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/42 | Diminta sejak MoM #2, ditagih Weekly #3. PIC Fathir belum masuk org.
Sprint 3 | Tim 05 | #44 | [F1-S3] US-13b · Scan sebelum tarik: pratinjau PDF baru vs sudah ada, pilih, lalu tarik | Moh. Rafli Gusti Saputra | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/44 | Keputusan 2 Weekly #3. Menyentuh mockup Ingest (#43).
Sprint 3 | Tim 05 | #47 | [F0-S3] US-11 · Lingkungan staging dan CI | Hamdancml | 4 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/47
Sprint 4 | Tim 05 | #28 | [F3] MITRA ISU-06 · Ambang kemiripan pasal untuk klasifikasi harmonisasi | Belum di-assign | 0 | Blocked | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/28 | MITRA — Dijawab kualitatif di rapat. Memblokir modul harmonisasi Fase 3. Tenggat 25 Okt.
Sprint 4 | Tim 05 | #32 | [F2-S4] US-01 · Manajemen pengguna dan peran | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/32 | Login & user management ditunda ke akhir proyek (Weekly #3). Standar OJK: LDAP + akun lokal + captcha.
Sprint 4 | Tim 05 | #37 | [F2-S4] US-29,30,31 · Versioning dokumen, pengelolaan dokumen, dan status keberlakuan | Moh. Rafli Gusti Saputra | 11 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/37 | Digeser dari Fase 1 — bukan indikator Fase 1.
Sprint 4 | Tim 05 | #48 | [F2-S4] US-04 · Toggle mode Deterministik / AI-Assisted | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/48
Sprint 4 | Tim 05 | #49 | [F2-S4] US-05 · Simpan hasil deterministik dan hasil AI terpisah | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/49
Sprint 4 | Tim 05 | #50 | [F2-S4] US-07 · Label "Draft / Rekomendasi" pada setiap output | Muhammad Ikhwan Ma'ruf Santoso | 2 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/50
Sprint 4 | Tim 05 | #51 | [F2-S4] US-32 · Parser struktur bab / pasal / ayat | Belum di-assign | 13 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/51 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 4 | Tim 05 | #52 | [F2-S4] US-33 · Ekstraksi dasar hukum yang dirujuk | Belum di-assign | 5 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/52 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 4 | Tim 05 | #53 | [F2-S4] US-34 · Status keberlakuan dokumen | Belum di-assign | 5 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/53 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 4 | Tim 05 | #54 | [F2-S4] US-64 · Rumusan aturan klasifikasi harmonisasi bersama mitra | Ahmad Zaky Ash Shidqi | 5 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/54
Sprint 5 | Tim 05 | #29 | [F4] MITRA OI-02 · Penunjukan pilot user Unit Bisnis IT | Ahmad Zaky Ash Shidqi | 0 | Blocked | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/29 | MITRA — Pilot user dibutuhkan untuk validasi template (M4) dan UAT. Tenggat 8 Nov.
Sprint 5 | Tim 05 | #30 | [F1-S3] US-17 · Baca dokumen dari folder OneDrive public | Moh. Rafli Gusti Saputra | 8 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/30 | Digeser ke Fase 2. Folder OneDrive sudah tersedia (#26 selesai, Weekly #3) — tidak lagi terblokir.
Sprint 5 | Tim 05 | #31 | [F2-S5] US-22 · OCR dokumen penuh untuk PDF hasil pindai | Belum di-assign | 8 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/31 | Digeser dari Fase 1 — OCR hal. 1 sudah dicakup US-20a.
Sprint 5 | Tim 05 | #33 | [F2-S5] US-03 · Beranda / dashboard | Muhammad Ikhwan Ma'ruf Santoso | 3 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/33 | Digeser dari Fase 1 — bukan indikator Fase 1.
Sprint 5 | Tim 05 | #34 | [F2-S5] US-08 · Audit log | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/34 | Digeser dari Fase 1. Audit log login sudah ada (MoM #2).
Sprint 5 | Tim 05 | #35 | [F2-S5] US-09 · Status pekerjaan berjalan | Muhammad Ikhwan Ma'ruf Santoso | 3 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/35 | Digeser dari Fase 1 — status ringkas sudah di US-14.
Sprint 5 | Tim 05 | #36 | [F2-S5] US-26a · Penyimpanan blok terstruktur di basis data | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/36 | Bergantung pada parser struktur pasal (US-32).
Sprint 5 | Tim 05 | #55 | [F2-S5] US-06 · Proses tetap selesai saat layanan AI mati | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/55
Sprint 5 | Tim 05 | #56 | [F2-S5] US-10 · Riwayat eksekusi analisa | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/56
Sprint 5 | Tim 05 | #57 | [F2-S5] US-35 · Ringkasan (summary) isi peraturan | Belum di-assign | 8 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/57 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 5 | Tim 05 | #58 | [F2-S5] US-36 · Key Takeaways bertautan pasal | Belum di-assign | 8 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/58 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 5 | Tim 05 | #59 | [F2-S5] US-37 · Lompat dari poin ringkasan ke teks pasal asli | Muhammad Ikhwan Ma'ruf Santoso | 5 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/59
Sprint 5 | Tim 05 | #60 | [F2-S5] US-38 · Identifikasi topik / klausul utama | Belum di-assign | 3 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/60 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 5 | Tim 05 | #61 | [F2-S5] US-39 · Waktu proses summary di bawah 5 menit | Belum di-assign | 3 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/61 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 5 | Tim 05 | #62 | [F2-S5] US-40 · Ekspor hasil analisa | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/62
Sprint 6 | Tim 05 | #63 | [F3-S6] US-41 · Jalankan harmonisasi draft terhadap knowledge base | Belum di-assign | 5 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/63 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 6 | Tim 05 | #64 | [F3-S6] US-42 · Pemilihan kandidat peraturan pembanding | Belum di-assign | 8 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/64 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 6 | Tim 05 | #65 | [F3-S6] US-43 · Pencocokan rujukan pasal eksplisit | Belum di-assign | 8 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/65 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 6 | Tim 05 | #66 | [F3-S6] US-44 · Deteksi rujukan ke peraturan yang telah dicabut | Belum di-assign | 5 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/66 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 6 | Tim 05 | #67 | [F3-S6] US-45 · Analisis kesesuaian makna antar pasal | Belum di-assign | 13 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/67 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 6 | Tim 05 | #68 | [F3-S6] US-46 · Klasifikasi temuan harmonisasi | Belum di-assign | 8 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/68 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 6 | Tim 05 | #69 | [F3-S6] US-47 · Atribut temuan: pasal, pembanding, jenis, keyakinan, kutipan | Belum di-assign | 3 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/69 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 6 | Tim 05 | #70 | [F3-S6] US-48 · Ringkasan hasil harmonisasi dan rekomendasi awal | Belum di-assign | 5 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/70 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 6 | Tim 05 | #71 | [F3-S6] US-49 · Penandaan temuan valid / tidak relevan | Muhammad Ikhwan Ma'ruf Santoso | 5 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/71
Sprint 6 | Tim 05 | #72 | [F3-S6] US-49a · Buka PDF asli dari temuan dan Key Takeaway | Muhammad Ikhwan Ma'ruf Santoso | 2 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/72
Sprint 6 | Tim 05 | #73 | [F3-S6] US-50 · Ekspor laporan harmonisasi | Moh. Rafli Gusti Saputra | 3 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/73
Sprint 6 | Tim 05 | #74 | [F3-S6] US-63 · Evaluasi recall deteksi harmonisasi | Ahmad Zaky Ash Shidqi | 3 | Todo | - | 2026-11-30 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/74
Sprint 7 | Tim 05 | #75 | [F4-S7] US-51 · Manajemen profil PoV unit fungsi | Moh. Rafli Gusti Saputra | 8 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/75
Sprint 7 | Tim 05 | #76 | [F4-S7] US-52 · Template tanggapan baku dan checklist pasal wajib | Moh. Rafli Gusti Saputra | 5 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/76
Sprint 7 | Tim 05 | #77 | [F4-S7] US-53 · Pemeriksaan kelengkapan pasal wajib ditanggapi | Belum di-assign | 5 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/77 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 7 | Tim 05 | #78 | [F4-S7] US-54 · Narasi draft tanggapan berbasis PoV | Belum di-assign | 13 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/78 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 7 | Tim 05 | #79 | [F4-S7] US-55 · Penyorotan pasal berdampak pada unit | Belum di-assign | 5 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/79 | PIC Fathir (mirzafathir) belum masuk org GitHub — belum bisa di-assign.
Sprint 7 | Tim 05 | #80 | [F4-S7] US-56 · Penyuntingan dan versioning draft tanggapan | Muhammad Ikhwan Ma'ruf Santoso | 5 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/80
Sprint 7 | Tim 05 | #81 | [F4-S7] US-57 · Struktur data PoV mendukung banyak profil | Moh. Rafli Gusti Saputra | 3 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/81
Sprint 7 | Tim 05 | #82 | [F4-S7] US-58 · Ekspor draft tanggapan sesuai format unit | Moh. Rafli Gusti Saputra | 3 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/82
Sprint 8 | Tim 05 | #1 | [F5-S8] US-02 · Login pengguna | Moh. Rafli Gusti Saputra | 3 | Todo | - | 2026-12-25 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/1 | Ditunda ke akhir proyek (Weekly #3): tanpa login, langsung dashboard. Kode JWT sudah ada — dimatikan dulu.
Sprint 8 | Tim 05 | #83 | [F5-S8] US-59 · Fallback test seluruh fitur tanpa layanan AI | Hamdancml | 5 | Todo | - | 2026-12-25 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/83
Sprint 8 | Tim 05 | #84 | [F5-S8] US-60 · UAT dengan pilot user per fitur | Hamdancml | 8 | Todo | - | 2026-12-25 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/84
Sprint 8 | Tim 05 | #85 | [F5-S8] US-61 · Panduan pengguna berbahasa Indonesia | Ahmad Zaky Ash Shidqi | 5 | Todo | - | 2026-12-25 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/85
Sprint 8 | Tim 05 | #86 | [F5-S8] US-62 · Dokumentasi teknis | Ahmad Zaky Ash Shidqi | 5 | Todo | - | 2026-12-25 | Belum jatuh tempo | 0 | https://github.com/hero-ojk-its/hero/issues/86
Sprint 1 | Tim 06 | (Draft) | Menyusun draft Project Requirement Document (PRD) | Aditya Fieansyah Putra Pratama | 0 | Done | - | 2026-09-28 | - | 0 | -
Sprint 1 | Tim 06 | (Draft) | Menyusun Project Charter | Aditya Fieansyah Putra Pratama | 0 | Done | - | 2026-09-28 | - | 0 | -
Sprint 1 | Tim 06 | (Draft) | Penandatanganan NDA anggota Tim | Aditya Fieansyah Putra Pratama | 0 | Done | - | 2026-09-28 | - | 0 | -
Sprint 2 | Tim 06 | (Draft) | Desain skema tabel dan ERD | Azhar Hafiz Andanianto | 8 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Setup project backend Golang | Azhar Hafiz Andanianto | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Deploy PostgreSQL di Kubernetes | Azhar Hafiz Andanianto | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | QA: pelajari arsitektur dan susun test plan Sprint 1 | Aditya Fieansyah Putra Pratama | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Deploy instance Zitadel | Jasmine Putri Alesyah | 8 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Rancang struktur project, aplikasi, dan role di Zitadel | Jasmine Putri Alesyah | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | QA: pelajari OIDC/SSO dan susun test plan Sprint 1 | Aditya Fieansyah Putra Pratama | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Deploy Kyverno di cluster | Rouli Elizabeth Geraldine Aritonang | 3 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Buat policy larangan image tag latest | Rouli Elizabeth Geraldine Aritonang | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Setup project frontend-web dan frontend-mobile | Dzikrina Hidayani Martin | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Susun design system dasar | Dzikrina Hidayani Martin | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Wireframe alur login dan pencarian | Dzikrina Hidayani Martin | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Konfigurasi Patroni (1 primary + 2 replika) | Azhar Hafiz Andanianto | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Seed data uji | Azhar Hafiz Andanianto | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | API CRUD order (CREATE, READ, UPDATE) | Azhar Hafiz Andanianto | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Tabel outbox_events | Azhar Hafiz Andanianto | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | QA: eksekusi test Sprint 1 | Aditya Fieansyah Putra Pratama | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Laporan Sprint 1 | Belum di-assign | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Integrasi OIDC di aplikasi web (backend) | Jasmine Putri Alesyah | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Endpoint logout | Jasmine Putri Alesyah | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | QA: eksekusi test Sprint 1 | Aditya Fieansyah Putra Pratama | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Laporan Sprint 1 | Belum di-assign | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Uji coba policy dengan deployment nginx | Rouli Elizabeth Geraldine Aritonang | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Verifikasi: policy Prevent (Kyverno) | Aditya Fieansyah Putra Pratama, Rouli Elizabeth Geraldine Aritonang | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Laporan Sprint 1 | Belum di-assign | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Halaman login web (redirect ke Zitadel) | Dzikrina Hidayani Martin | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Halaman utama dan kerangka hasil pencarian | Dzikrina Hidayani Martin | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | QA: review wireframe dan susun test plan Sprint 1 | Aditya Fieansyah Putra Pratama | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | QA: eksekusi test Sprint 1 | Belum di-assign | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 06 | (Draft) | Laporan Sprint 1 | Belum di-assign | 0 | Todo | - | 2026-10-12 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Deploy Kafka dan desain topic | Azhar Hafiz Andanianto | 13 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Kafka Connect + Debezium connector | Azhar Hafiz Andanianto | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Deploy OpenSearch, Dashboards, dan index orders | Azhar Hafiz Andanianto | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | QA: pelajari CDC dan susun test plan Sprint 2 | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Integrasi OIDC di aplikasi mobile | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Verifikasi SSO lintas aplikasi | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | QA: pelajari passkey/WebAuthn dan susun test plan Sprint 2 | Belum di-assign | 5 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Deploy cert-manager | Belum di-assign | 3 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Buat ClusterIssuer Let's Encrypt | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Halaman login aplikasi mobile | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Uji dan sesuaikan pengalaman SSO lintas aplikasi | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Pipeline Data Prepper (Kafka → OpenSearch) | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Tangani event create vs update | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Verifikasi sinkronisasi dan ukur jeda | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | QA: eksekusi test Sprint 2 + retest bug Sprint 1 | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Laporan Sprint 2 | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Aktifkan dan konfigurasi passkey di Zitadel | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Alur registrasi dan login passkey di aplikasi mobile | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | QA: eksekusi test Sprint 2 + retest bug Sprint 1 | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Laporan Sprint 2 | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Terbitkan sertifikat untuk web.devom.silog.co.id | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Terbitkan sertifikat untuk api.devom.silog.co.id | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Verifikasi: sertifikat TLS otomatis | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Laporan Sprint 2 | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | UI registrasi dan login passkey | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | QA: susun test plan Sprint 2 | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | QA: eksekusi test Sprint 2 + retest bug Sprint 1 | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 06 | (Draft) | Laporan Sprint 2 | Belum di-assign | 0 | Todo | - | 2026-10-26 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Endpoint GET /api/searchorder | Belum di-assign | 5 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Highlight kata kunci | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Perluas index untuk tenant dan gudang | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | QA: susun test plan Sprint 3 | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Konfigurasi login password untuk staff office | Belum di-assign | 5 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Aktifkan TOTP sebagai faktor kedua | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | QA: susun test plan Sprint 3 (step-up auth) | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Deploy Trivy di pipeline CI/CD | Belum di-assign | 5 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Tentukan security gate (severity HIGH/CRITICAL) | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Sambungkan pencarian ke API /api/searchorder | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Paginasi hasil pencarian | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Fuzzy matching (typo tolerance) | Belum di-assign | 3 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Pengurutan hasil (sort by description) | Belum di-assign | 1 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Dokumentasi API pencarian | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | QA: eksekusi test Sprint 3 + retest bug | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Laporan Sprint 3 | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Mekanisme step-up authentication di backend | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | UI staff office: login dan verifikasi TOTP | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | QA: eksekusi test Sprint 3 + retest bug | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Laporan Sprint 3 | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Laporan hasil scanning dan cara membacanya | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Scan seluruh image yang sudah dideploy | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Verifikasi: security gate Trivy | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Laporan Sprint 3 | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Halaman login password untuk staff office | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Modal verifikasi TOTP saat transaksi sensitif | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | QA: susun test plan Sprint 3 | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | QA: eksekusi test Sprint 3 + retest bug | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 06 | (Draft) | Laporan Sprint 3 | Belum di-assign | 0 | Todo | - | 2026-11-09 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Mapping autocomplete | Belum di-assign | 5 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Endpoint autocomplete | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA: susun test plan Sprint 4 dan skenario beban | Belum di-assign | 5 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Konfigurasi SMTP untuk notifikasi email | Belum di-assign | 5 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Riset dan pilih platform instant messaging | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA: susun test plan Sprint 4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Deploy Falco di cluster | Belum di-assign | 5 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Buat custom rule deteksi akses /etc/shadow | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Autocomplete pada search bar | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Kontrol pengurutan hasil | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA: susun test plan Sprint 4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Skenario stress test JMeter | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Jalankan stress test dan optimasi | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA: eksekusi test Sprint 4 + stress test independen | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan Sprint 4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Kirim notifikasi login dari perangkat baru | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Integrasi notifikasi instant messaging | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA: eksekusi test Sprint 4 + retest bug | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan Sprint 4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Uji deteksi dan format alert | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Siapkan tempat melihat alert (log/dashboard) | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Verifikasi: deteksi Falco | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan Sprint 4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Halaman preferensi notifikasi | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Uji responsif dan aksesibilitas dasar | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA: eksekusi test Sprint 4 + retest bug | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan Sprint 4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Perbaikan sisa bug Sprint 1–4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Uji failover saat ada beban | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Dokumentasi teknis dan runbook | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Merge ke branch utama dan code freeze | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA: regression test Sprint 1–4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan Sprint 5 (code freeze) | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Perbaikan sisa bug Sprint 1–4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Uji ulang SSO dan session expiry | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Dokumentasi teknis dan runbook IAM | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Merge ke branch utama dan code freeze | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA: regression test Sprint 1–4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan Sprint 5 (code freeze) | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Deploy Velero dan konfigurasi backup storage | Belum di-assign | 8 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Buat jadwal backup otomatis | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Uji simulasi kehilangan data dan restore | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Dokumentasi teknis dan runbook security stack | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Merge manifest ke branch utama dan code freeze | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Verifikasi: regression seluruh security stack | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan Sprint 5 (code freeze) | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Perbaikan sisa bug Sprint 1–4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Penanganan error dan pesan yang konsisten | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Dokumentasi teknis dan panduan UI | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Merge ke branch utama dan code freeze | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA: regression test Sprint 1–4 | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan Sprint 5 (code freeze) | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: uji menyeluruh semua kriteria penerimaan | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: laporan temuan dan prioritas revisi | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: uji menyeluruh semua kriteria penerimaan | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: laporan temuan dan prioritas revisi | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: uji menyeluruh semua kriteria penerimaan | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: laporan temuan dan prioritas revisi | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: uji menyeluruh seluruh alur UI | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: laporan temuan dan prioritas revisi | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: retest revisi dan regression akhir | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan akhir dan demo fitur pencarian | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: retest revisi dan regression akhir | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan akhir dan demo fitur IAM | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: retest revisi dan regression akhir | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan akhir dan demo security stack | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | QA Final: retest revisi dan regression akhir | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | (Draft) | Laporan akhir dan demo UI | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 06 | #131 | la | Belum di-assign | 0 | Todo | - | 2026-12-14 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/131
Sprint 1 | Tim 07 | #24 | Onboarding ke repository DPTSI | Siti Zahra Ananda Kurniawan | 1 | Done | - | 2026-09-22 | - | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/24 | Masih perlu akses ke repo Portal ITS Mobile
Sprint 1 | Tim 07 | #26 | Requirement gathering | Sinta Probondari Wardani | 3 | Done | - | 2026-09-22 | - | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/26
Sprint 1 | Tim 07 | #27 | Drafting PRD dan Project Charter | Siti Zahra Ananda Kurniawan | 3 | Done | - | 2026-09-22 | - | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/27
Sprint 1 | Tim 07 | #30 | Drafting dan finalisasi PRD dan Project Charter | Siti Zahra Ananda Kurniawan | 2 | Blocked | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/30 | Masih belum mendapatkan resp dari Pak Baskoro
Sprint 1 | Tim 07 | #129 | [Analyst] Dokumentasi kebutuhan, aktor, dan alur presensi rapat | Sinta Probondari Wardani | 3 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/129
Sprint 1 | Tim 07 | #116 | [Frontend] Membuat wireframe alur presensi peserta | Siti Zahra Ananda Kurniawan | 2 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/116
Sprint 1 | Tim 07 | #117 | [Backend] Menyusun API contract presensi rapat | Muhammad Surya Yasar | 2 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/117
Sprint 1 | Tim 07 | #119 | [Backend] Membuat model data rapat dan undangan | Muhammad Surya Yasar | 3 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/119
Sprint 1 | Tim 07 | #122 | [Backend] Menentukan dan menerapkan lifecycle sesi rapat | Muhammad Surya Yasar | 2 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/122
Sprint 1 | Tim 07 | #123 | [Backend] Mendefinisikan konfigurasi integrasi SSO ITS | Muhammad Surya Yasar | 2 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/123
Sprint 1 | Tim 07 | #125 | [Backend] Memetakan identitas dan role pengguna dari SSO | Muhammad Surya Yasar | 2 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/125
Sprint 1 | Tim 07 | #118 | [Infra-QA] Menyiapkan konfigurasi environment backend Go | adeliarahmaa | 2 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/118
Sprint 1 | Tim 07 | #127 | [Infra-QA] Membuat pipeline CI untuk backend Go | adeliarahmaa | 3 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/127
Sprint 1 | Tim 07 | #128 | [Infra-QA] Menyiapkan deployment backend ke staging | adeliarahmaa | 3 | Todo | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/128
Sprint 2 | Tim 07 | #120 | [Backend] Menambahkan endpoint detail dan status sesi rapat | Muhammad Surya Yasar | 2 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/120
Sprint 2 | Tim 07 | #121 | [Backend] Membuat endpoint pembuatan sesi rapat | Muhammad Surya Yasar | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/121
Sprint 2 | Tim 07 | #124 | [Backend] Mengimplementasikan login melalui SSO ITS | Muhammad Surya Yasar | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/124
Sprint 2 | Tim 07 | #126 | [Frontend] Membuat layar pembuka presensi melalui tautan | Siti Zahra Ananda Kurniawan | 2 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/126
Sprint 2 | Tim 07 | (Draft) | [Frontend] Membuat formulir data presensi peserta | Belum di-assign | 2 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 07 | (Draft) | [Frontend] Membuat layar hasil pengiriman presensi | Belum di-assign | 1 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 2 | Tim 07 | (Draft) | [Frontend] Membuat layar daftar rapat milik pengundang | Belum di-assign | 2 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Backend] Membuat generator tautan presensi rapat | Belum di-assign | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Backend] Menambahkan validasi masa berlaku tautan presensi | Belum di-assign | 1 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Backend] Membuat endpoint validasi tautan presensi | Belum di-assign | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Backend] Menentukan format payload QR code presensi | Belum di-assign | 1 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Backend] Membuat endpoint validasi QR code presensi | Belum di-assign | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Backend] Mengimplementasikan validasi lokasi presensi luring | Belum di-assign | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Backend] Mencatat alasan kegagalan validasi QR dan lokasi | Belum di-assign | 1 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Frontend] Membuat UI pemeriksaan dan validasi daftar hadir | Belum di-assign | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Frontend] Membuat tampilan rekap kehadiran rapat | Belum di-assign | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Frontend] Mengintegrasikan autentikasi SSO pada alur presensi | Belum di-assign | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Frontend] Mengimplementasikan pemindaian QR code presensi | Belum di-assign | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Frontend] Mengintegrasikan pengambilan lokasi peserta | Belum di-assign | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Frontend] Menangani error presensi berbasis lokasi | Belum di-assign | 1 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Frontend] Menambahkan refresh data rekap kehadiran | Belum di-assign | 1 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Infra-QA] Menyusun test case fungsional per mode rapat | Belum di-assign | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Infra-QA] Menguji autentikasi dan otorisasi aplikasi | Belum di-assign | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Infra-QA] Menguji validasi tautan, QR code, dan lokasi | Belum di-assign | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 3 | Tim 07 | (Draft) | [Infra-QA] Melakukan pengujian keamanan dasar API | Belum di-assign | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 07 | (Draft) | [Backend] Membuat endpoint daftar hadir untuk proses validasi | Belum di-assign | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 07 | (Draft) | [Backend] Membuat endpoint persetujuan daftar hadir | Belum di-assign | 2 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 07 | (Draft) | [Backend] Mendokumentasikan kontrak integrasi MyITS Sign | Belum di-assign | 2 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 07 | (Draft) | [Backend] Membuat generator PDF daftar hadir | Belum di-assign | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 07 | (Draft) | [Backend] Mengirim PDF daftar hadir ke MyITS Sign | Belum di-assign | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 07 | (Draft) | [Backend] Menangani status dan callback TTE | Belum di-assign | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 07 | (Draft) | [Frontend] Menampilkan status TTE dan unduh dokumen | Belum di-assign | 1 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 4 | Tim 07 | (Draft) | [Infra-QA] Menyiapkan data dan akun uji piloting | Belum di-assign | 2 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 07 | (Draft) | [Analyst] Mendampingi piloting/testing dan mengumpulkan feedback | Belum di-assign | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 07 | (Draft) | [Analyst] Menyusun dokumentasi teknis dan panduan pengguna | Belum di-assign | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 5 | Tim 07 | (Draft) | [Analyst] Menyusun laporan evaluasi dan laporan akhir proyek (gabungan) | Belum di-assign | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | -
Sprint 1 | Tim 08 | #21 | Membuat NDA | Nabil Jamal Sungkar, Akhmad Mustofa Solikin, Tarisha Falah Basuki | 0 | Done | 2026-09-25 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/21 | https://itsacid-my.sharepoint.com/:f:/g/personal/5025211230_student_its_ac_id/IgCfkzLZr3kSRZDSIOMPOdpIAQtj0oXXV6A-y3pdH238fF4?e=d3hjmq
Sprint 1 | Tim 08 | #11 | Membuat PRD | Akhmad Mustofa Solikin, Tarisha Falah Basuki | 0 | Done | 2026-09-25 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/11 | https://itsacid-my.sharepoint.com/:w:/g/personal/5025211230_student_its_ac_id/IQDyHLc9mBWuQqe_OKBVwymuAf54twfr8kQy_THnXeNcVL8?e=MX1XDz
Sprint 1 | Tim 08 | #13 | Membuat Project Charter | Tarisha Falah Basuki | 0 | Done | 2026-09-25 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/13 | https://itsacid-my.sharepoint.com/:w:/g/personal/5025211230_student_its_ac_id/IQAJFffHz6XRQ5Ll0pWjwkwpAdLebRk--0-nI6pqzEmTD0I?e=kEWFdO
Sprint 1 | Tim 08 | #12 | Setup Bitbucket | Tarisha Falah Basuki | 0 | Done | 2026-09-25 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/12 | https://bitbucket.org/dptsi/myits-beasiswa-asih-datamodel/src/master/
Sprint 1 | Tim 08 | #20 | Dokumentasi Requirement dan Perubahan Refactor Beasiswa ASIH | Akhmad Mustofa Solikin, Tarisha Falah Basuki | 0 | Done | 2026-09-25 | 2026-09-26 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/20 | https://itsacid-my.sharepoint.com/:w:/g/personal/5025211230_student_its_ac_id/IQDeJHdq_M6OT7j4NDPfTCWEAfZ87XW3WT6Q8390EDiFihM?e=wtixeu
Sprint 2 | Tim 08 | #14 | Setup & Konfigurasi Repository Project | Nabil Jamal Sungkar, Akhmad Mustofa Solikin, Tarisha Falah Basuki | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/14
Sprint 2 | Tim 08 | #15 | FE: Implementasi Global Layout, Navbar, Sidebar, dan Navigation | Tarisha Falah Basuki | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/15
Sprint 2 | Tim 08 | #16 | FE: Implementasi UI Authentication berdasarkan Role Pengguna | Tarisha Falah Basuki | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/16
Sprint 2 | Tim 08 | #17 | FE: Implementasi UI Login SSO Mahasiswa dan User Internal | Tarisha Falah Basuki | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/17
Sprint 2 | Tim 08 | #18 | FE: Implementasi UI Login Manual untuk User Eksternal | Tarisha Falah Basuki | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/18
Sprint 2 | Tim 08 | #19 | FE: Implementasi Role-based Navigation untuk Mahasiswa, Ortu Asuh, dan Admin | Tarisha Falah Basuki | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/19
Sprint 2 | Tim 08 | #40 | BE: Implementasi Authentication SSO untuk Mahasiswa dan User Internal | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/40
Sprint 2 | Tim 08 | #41 | BE: Implementasi Authentication Manual untuk User Eksternal | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/41
Sprint 2 | Tim 08 | #42 | BE: Implementasi Role dan Authorization Pengguna | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/42
Sprint 2 | Tim 08 | #43 | BE: Implementasi Authentication Alumni | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/43
Sprint 2 | Tim 08 | #44 | BE: Implementasi API Authentication dan Session Management | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/44
Sprint 2 | Tim 08 | #77 | BE: Analisis Struktur Database MySQL | Nabil Jamal Sungkar | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/77
Sprint 2 | Tim 08 | #78 | BE: Perancangan Database PostgreSQL | Nabil Jamal Sungkar | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/78
Sprint 2 | Tim 08 | #79 | BE: Migrasi Database MySQL ke PostgreSQL | Nabil Jamal Sungkar | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/79
Sprint 2 | Tim 08 | #80 | BE: Penyesuaian Konfigurasi Backend ke PostgreSQL | Nabil Jamal Sungkar | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/80
Sprint 2 | Tim 08 | #81 | BE: Validasi Data dan Database setelah Migrasi | Nabil Jamal Sungkar | 0 | Todo | - | 2026-10-10 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/81
Sprint 3 | Tim 08 | #22 | FE: Implementasi UI Halaman Informasi dan Detail Bantuan Mahasiswa | Tarisha Falah Basuki | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/22
Sprint 3 | Tim 08 | #23 | FE: Implementasi UI Form Data Mahasiswa dan Biaya Hidup | Tarisha Falah Basuki | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/23
Sprint 3 | Tim 08 | #24 | FE: Implementasi UI Status Penerimaan dan Status Bantuan Mahasiswa | Tarisha Falah Basuki | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/24
Sprint 3 | Tim 08 | #25 | FE: Implementasi UI Halaman Konfirmasi Penerimaan Bantuan Mahasiswa | Tarisha Falah Basuki | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/25
Sprint 3 | Tim 08 | #45 | BE: Implementasi API Data Mahasiswa | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/45
Sprint 3 | Tim 08 | #46 | BE: Implementasi API Informasi dan Detail Bantuan Mahasiswa | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/46
Sprint 3 | Tim 08 | #47 | BE: Implementasi API Status Penerimaan dan Status Bantuan | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/47
Sprint 3 | Tim 08 | #48 | BE: Implementasi API Konfirmasi Penerimaan Bantuan | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/48
Sprint 3 | Tim 08 | #49 | BE: Implementasi Validasi Konfirmasi Penerimaan Bantuan | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/49
Sprint 3 | Tim 08 | #83 | BE: Implementasi Auto-Confirm Penerimaan Bantuan | Nabil Jamal Sungkar | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/83
Sprint 3 | Tim 08 | #50 | BE: Implementasi Notifikasi Email Konfirmasi Bantuan | Nabil Jamal Sungkar | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/50
Sprint 3 | Tim 08 | #52 | BE: Penyesuaian Data Bantuan tanpa Komponen UKT | Nabil Jamal Sungkar | 0 | Todo | - | 2026-10-24 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/52
Sprint 4 | Tim 08 | #26 | FE: Implementasi UI Daftar dan Detail Mahasiswa Penerima | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/26
Sprint 4 | Tim 08 | #27 | FE: Implementasi Flow Pemilihan Mahasiswa Penerima oleh Orang Tua Asuh | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/27
Sprint 4 | Tim 08 | #28 | FE: Implementasi UI Form Detail Pemberian Bantuan oleh Orang Tua Asuh | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/28
Sprint 4 | Tim 08 | #29 | FE: Implementasi UI Upload Bukti Pemberian Bantuan oleh Orang Tua Asuh | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/29
Sprint 4 | Tim 08 | #30 | FE: Implementasi UI Manajemen Data Penerima oleh Admin | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/30
Sprint 4 | Tim 08 | #31 | FE: Implementasi Flow Seleksi dan Penetapan Penerima oleh Admin | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/31
Sprint 4 | Tim 08 | #32 | FE: Implementasi UI Manajemen Bantuan dan Periode Bantuan oleh Admin | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/32
Sprint 4 | Tim 08 | #33 | FE: Implementasi UI Upload Bukti Pemberian Bantuan oleh Admin | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/33
Sprint 4 | Tim 08 | #51 | BE: Implementasi API Daftar dan Detail Mahasiswa Penerima | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/51
Sprint 4 | Tim 08 | #53 | BE: Implementasi API Pemilihan Penerima oleh Orang Tua Asuh | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/53
Sprint 4 | Tim 08 | #54 | BE: Implementasi API Penyerahan Pemilihan Penerima kepada Ditmawa | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/54
Sprint 4 | Tim 08 | #55 | BE: Implementasi API Pemberian Bantuan oleh Orang Tua Asuh | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/55
Sprint 4 | Tim 08 | #56 | BE: Implementasi Pengelolaan Periode Bantuan | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/56
Sprint 4 | Tim 08 | #57 | BE: Implementasi API Upload Bukti Transfer oleh Orang Tua Asuh | Nabil Jamal Sungkar | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/57
Sprint 4 | Tim 08 | #58 | BE: Implementasi API Upload Bukti Transfer oleh Admin | Nabil Jamal Sungkar | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/58
Sprint 4 | Tim 08 | #59 | BE: Implementasi API Manajemen Data Penerima oleh Admin | Nabil Jamal Sungkar | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/59
Sprint 4 | Tim 08 | #60 | BE: Implementasi API Seleksi dan Penetapan Penerima oleh Admin | Nabil Jamal Sungkar | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/60
Sprint 4 | Tim 08 | #61 | BE: Implementasi Status Proses Bantuan | Nabil Jamal Sungkar | 0 | Todo | - | 2026-11-07 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/61
Sprint 5 | Tim 08 | #34 | FE: Implementasi UI Halaman Rekapitulasi Bantuan | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/34
Sprint 5 | Tim 08 | #35 | FE: Implementasi Download Rekapitulasi Bantuan | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/35
Sprint 5 | Tim 08 | #36 | FE: Implementasi UI Notification State Bukti Pemberian Bantuan | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/36
Sprint 5 | Tim 08 | #37 | FE: Implementasi UI Filter, Search Bar untuk Data Penerima dan Rekapitulasi Bantuan | Tarisha Falah Basuki | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/37
Sprint 5 | Tim 08 | #62 | BE: Implementasi API Rekapitulasi Bantuan | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/62
Sprint 5 | Tim 08 | #63 | BE: Implementasi Rekapitulasi Data Orang Tua Asuh | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/63
Sprint 5 | Tim 08 | #64 | BE: Implementasi Filter Rekapitulasi Berdasarkan Periode | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/64
Sprint 5 | Tim 08 | #65 | BE: Implementasi Filter Data Berdasarkan Status | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/65
Sprint 5 | Tim 08 | #66 | BE: Implementasi API Search Data Penerima dan Bantuan | Nabil Jamal Sungkar | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/66
Sprint 5 | Tim 08 | #67 | BE: Implementasi Export Rekapitulasi ke Excel | Nabil Jamal Sungkar | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/67
Sprint 5 | Tim 08 | #68 | BE: Implementasi Status dan Notifikasi Bukti Transfer | Nabil Jamal Sungkar | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/68
Sprint 5 | Tim 08 | #69 | BE: Implementasi Pengingat Pembayaran Berikutnya | Nabil Jamal Sungkar | 0 | Todo | - | 2026-11-21 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/69
Sprint 6 | Tim 08 | #38 | FE: Implementasi dan penyempurnaan Responsive UI | Tarisha Falah Basuki | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/38
Sprint 6 | Tim 08 | #39 | FE: Frontend Functional Testing seluruh Role | Tarisha Falah Basuki | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/39
Sprint 6 | Tim 08 | #70 | BE: Automated Testing Modul Kritis | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/70
Sprint 6 | Tim 08 | #71 | BE: Integration Testing API | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/71
Sprint 6 | Tim 08 | #72 | BE: Backend Functional Testing seluruh Role | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/72
Sprint 6 | Tim 08 | #73 | BE: Validasi Role dan Access Control | Akhmad Mustofa Solikin | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/73
Sprint 6 | Tim 08 | #74 | BE: Bug Fixing dan Penyempurnaan API | Nabil Jamal Sungkar, Akhmad Mustofa Solikin, Tarisha Falah Basuki | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/74
Sprint 6 | Tim 08 | #75 | BE: Optimasi Query dan Performa Database | Nabil Jamal Sungkar, Akhmad Mustofa Solikin | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/75
Sprint 6 | Tim 08 | #76 | BE: Dokumentasi API | Nabil Jamal Sungkar, Akhmad Mustofa Solikin, Tarisha Falah Basuki | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/76
Sprint 6 | Tim 08 | #84 | BE: Dokumentasi Arsitektur dan Struktur Backend | Nabil Jamal Sungkar, Akhmad Mustofa Solikin, Tarisha Falah Basuki | 0 | Todo | - | 2026-12-05 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-0-Backend/issues/84
Sprint 1 | Tim 09 | #31 | Meeting dengan DPTSI | Muhammad Irsyad Habibi, Keisha Syabilla Alia Ghifarani | 0 | Done | 2026-09-04 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/31
Sprint 1 | Tim 09 | #32 | Meeting dengan Ditmawa & Medical Center | Achmad Hasan Al Fikri, Keisha Syabilla Alia Ghifarani | 0 | Done | 2026-09-09 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/32
Sprint 1 | Tim 09 | #41 | Pengisian dan Penandatanganan Non-Disclosure Agreement (NDA) | Keisha Syabilla Alia Ghifarani | 0 | Done | 2026-09-14 | 2026-09-22 | Tepat waktu | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/41
Sprint 1 | Tim 09 | #33 | Membuat User Story | Achmad Hasan Al Fikri | 2 | Done | 2026-09-23 | 2026-09-22 | Terlambat | 1 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/33
Sprint 1 | Tim 09 | #34 | Membuat User Flow | Achmad Hasan Al Fikri | 2 | Done | 2026-09-23 | 2026-09-22 | Terlambat | 1 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/34
Sprint 1 | Tim 09 | #35 | Membuat Timeline & RAB | Keisha Syabilla Alia Ghifarani | 1 | Done | 2026-09-23 | 2026-09-22 | Terlambat | 1 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/35
Sprint 1 | Tim 09 | #36 | Menyusun Project Charter | Keisha Syabilla Alia Ghifarani | 2 | Done | 2026-09-24 | 2026-09-22 | Terlambat | 2 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/36
Sprint 1 | Tim 09 | #37 | Menyusun Product Requirement Document | Keisha Syabilla Alia Ghifarani | 3 | Done | 2026-09-24 | 2026-09-22 | Terlambat | 2 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/37
Sprint 1 | Tim 09 | #38 | Validasi & Finalisasi User Story | Achmad Hasan Al Fikri | 1 | In progress | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/38 | Masih menunggu TTD & Revisi dari DPTSI.
Sprint 1 | Tim 09 | #39 | Validasi & Finalisasi User Flow | Achmad Hasan Al Fikri | 1 | In progress | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/39 | Masih menunggu TTD & Revisi dari DPTSI.
Sprint 1 | Tim 09 | #40 | Finalisasi Project Charter & PRD | Keisha Syabilla Alia Ghifarani | 1 | In progress | - | 2026-09-22 | Terlambat | 8 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/40 | Masih menunggu TTD & Revisi dari DPTSI.
Sprint 2 | Tim 09 | #42 | UI/UX - Dashboard Mahasiswa | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/42
Sprint 2 | Tim 09 | #43 | UI/UX - Screening Page | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/43
Sprint 2 | Tim 09 | #44 | UI/UX - Booking SVARA Page | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/44
Sprint 2 | Tim 09 | #45 | UI/UX - Journaling Page | Keisha Syabilla Alia Ghifarani | 1 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/45
Sprint 2 | Tim 09 | #46 | UI/UX - Dashboard Psikolog | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/46
Sprint 2 | Tim 09 | #49 | UI/UX - Detail Kasus Mahasiswa | Keisha Syabilla Alia Ghifarani | 1 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/49
Sprint 2 | Tim 09 | #50 | UI/UX - Kelola Jadwal SVARA | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/50
Sprint 2 | Tim 09 | #51 | UI/UX - Kelola Booking SVARA | Keisha Syabilla Alia Ghifarani | 1 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/51
Sprint 2 | Tim 09 | #52 | UI/UX - Dashboard SVARA | Keisha Syabilla Alia Ghifarani | 1 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/52
Sprint 2 | Tim 09 | #53 | UI/UX - Detail Konsultasi SVARA | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/53
Sprint 2 | Tim 09 | #54 | UI/UX - Dashboard dan Observasi Ditmawa | Keisha Syabilla Alia Ghifarani | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/54
Sprint 2 | Tim 09 | #55 | AN - Review UI/UX dan User Flow | Achmad Hasan Al Fikri | 2 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/55
Sprint 2 | Tim 09 | #56 | AN - Validasi dan Finalisasi UI/UX | Achmad Hasan Al Fikri, Keisha Syabilla Alia Ghifarani | 1 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/56
Sprint 2 | Tim 09 | #57 | BE - Review Existing Database & ERD | Ahmad Muqorrobin | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/57 | Database dari Bitbucket DPTSI.
Sprint 2 | Tim 09 | #59 | BE - Perancangan Arsitektur dan Hak Akses | Ahmad Muqorrobin | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/59
Sprint 2 | Tim 09 | #60 | PL - Review Repository dan Infrastruktur | Muhammad Irsyad Habibi | 1 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/60 | Repository dari Bitbucket DPTSI.
Sprint 2 | Tim 09 | #61 | PL - Setup Docker | Muhammad Irsyad Habibi | 2 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/61
Sprint 2 | Tim 09 | #62 | PL - Persiapan CI/CD dan Integrasi myITS Portal | Muhammad Irsyad Habibi, Ahmad Muqorrobin | 3 | Todo | - | 2026-10-06 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/62
Sprint 3 | Tim 09 | #63 | FE - Dashboard Mahasiswa | Keisha Syabilla Alia Ghifarani | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/63
Sprint 3 | Tim 09 | #64 | FE - Screening Page | Keisha Syabilla Alia Ghifarani | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/64
Sprint 3 | Tim 09 | #72 | FE - Journaling Page | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/72
Sprint 3 | Tim 09 | #65 | BE - Autentikasi dan Hak Akses | Ahmad Muqorrobin | 5 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/65
Sprint 3 | Tim 09 | #66 | BE - Screening dan Skoring Kategori | Ahmad Muqorrobin | 5 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/66
Sprint 3 | Tim 09 | #67 | BE - Informed Consent dan Draft Screening | Ahmad Muqorrobin | 2 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/67
Sprint 3 | Tim 09 | #68 | BE - Hasil Screening | Ahmad Muqorrobin | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/68
Sprint 3 | Tim 09 | #95 | BE - Pengelolaan Journaling | Ahmad Muqorrobin | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/95
Sprint 3 | Tim 09 | #69 | AN - Review Dashboard Mahasiswa, Screening & Journaling | Achmad Hasan Al Fikri | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/69
Sprint 3 | Tim 09 | #70 | PL - Konfigurasi CI/CD | Muhammad Irsyad Habibi | 3 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/70
Sprint 3 | Tim 09 | #71 | PL - Integrasi Environment Pengembangan | Muhammad Irsyad Habibi | 2 | Todo | - | 2026-10-20 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/71
Sprint 4 | Tim 09 | #73 | FE - Booking SVARA Page | Keisha Syabilla Alia Ghifarani | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/73
Sprint 4 | Tim 09 | #74 | FE - Kelola Jadwal SVARA | Keisha Syabilla Alia Ghifarani | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/74
Sprint 4 | Tim 09 | #75 | FE - Kelola Booking SVARA | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/75
Sprint 4 | Tim 09 | #76 | FE - Dashboard SVARA | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/76
Sprint 4 | Tim 09 | #77 | BE - Pengelolaan Jadwal dan Slot SVARA | Ahmad Muqorrobin | 5 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/77
Sprint 4 | Tim 09 | #78 | BE - Booking dan Reschedule SVARA | Ahmad Muqorrobin | 5 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/78
Sprint 4 | Tim 09 | #79 | BE - Riwayat Booking dan Preferensi Petugas | Ahmad Muqorrobin | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/79
Sprint 4 | Tim 09 | #80 | BE - List Booking SVARA | Ahmad Muqorrobin | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/80
Sprint 4 | Tim 09 | #81 | AN - Review SVARA Booking | Achmad Hasan Al Fikri | 3 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/81
Sprint 4 | Tim 09 | #82 | PL - Integrasi Modul SVARA | Muhammad Irsyad Habibi | 2 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/82
Sprint 4 | Tim 09 | #105 | PL - Pembaruan Konfigurasi CI/CD | Muhammad Irsyad Habibi | 1 | Todo | - | 2026-11-03 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/105
Sprint 5 | Tim 09 | #83 | FE - Detail Konsultasi SVARA | Keisha Syabilla Alia Ghifarani | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/83
Sprint 5 | Tim 09 | #84 | FE - Dashboard Psikolog | Keisha Syabilla Alia Ghifarani | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/84
Sprint 5 | Tim 09 | #85 | FE - Detail Kasus Mahasiswa | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/85
Sprint 5 | Tim 09 | #86 | FE - Dashboard dan Observasi Ditmawa | Keisha Syabilla Alia Ghifarani | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/86
Sprint 5 | Tim 09 | #87 | BE - Pengelolaan Sesi Konsultasi SVARA | Ahmad Muqorrobin | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/87
Sprint 5 | Tim 09 | #88 | BE - Pengelolaan Pool Kasus dan Eskalasi | Ahmad Muqorrobin | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/88
Sprint 5 | Tim 09 | #89 | BE - Pengelolaan Kasus Merah dan Status Kunjungan | Ahmad Muqorrobin | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/89
Sprint 5 | Tim 09 | #90 | BE - Pengelolaan Observasi Ditmawa | Ahmad Muqorrobin | 5 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/90
Sprint 5 | Tim 09 | #91 | AN - Review Konsultasi Psikolog dan Observasi Ditmawa | Achmad Hasan Al Fikri | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/91
Sprint 5 | Tim 09 | #132 | PL - Integrasi Modul Konsultasi dan Kasus | Muhammad Irsyad Habibi | 2 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/132
Sprint 5 | Tim 09 | #106 | PL - Pembaruan Konfigurasi CI/CD | Muhammad Irsyad Habibi | 1 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/106
Sprint 5 | Tim 09 | #92 | PL - Persiapan Integrasi myITS Portal | Muhammad Irsyad Habibi | 3 | Todo | - | 2026-11-17 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/92
Sprint 6 | Tim 09 | #93 | FE - Sharing Journaling | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/93
Sprint 6 | Tim 09 | #94 | FE - Notifikasi dan Feedback | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/94
Sprint 6 | Tim 09 | #96 | BE - Pengelolaan Akses Journaling | Ahmad Muqorrobin | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/96
Sprint 6 | Tim 09 | #97 | BE - Integrasi Notifikasi myITS Mobile | Ahmad Muqorrobin | 5 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/97
Sprint 6 | Tim 09 | #107 | BE - Finalisasi Integrasi dan Hak Akses | Ahmad Muqorrobin | 5 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/107
Sprint 6 | Tim 09 | #98 | BE - Pengelolaan Feedback SVARA | Ahmad Muqorrobin | 2 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/98
Sprint 6 | Tim 09 | #99 | AN - Pengujian Keseluruhan Sistem | Achmad Hasan Al Fikri | 8 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/99
Sprint 6 | Tim 09 | #100 | AN - Penyusunan Skenario UAT | Achmad Hasan Al Fikri | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/100
Sprint 6 | Tim 09 | #101 | PL - Persiapan Environment UAT | Muhammad Irsyad Habibi | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/101
Sprint 6 | Tim 09 | #104 | PL - Deployment Akhir dan Integrasi myITS Portal | Muhammad Irsyad Habibi | 5 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/104
Sprint 6 | Tim 09 | #133 | Persiapan UAT | Keisha Syabilla Alia Ghifarani | 2 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/133
Sprint 6 | Tim 09 | #134 | Penyusunan Laporan Akhir | Keisha Syabilla Alia Ghifarani | 3 | Todo | - | 2026-12-01 | Belum jatuh tempo | 0 | https://github.com/if-capstone-26/Capstone-07-Portal-ITS-Mobile-DPTSI/issues/134

## Rekap Tim
Sprint | Tim | SP Assigned | SP Done | Progress (%) | Task Done | Task Terlambat | Commit | Status Tim | Catatan
Sprint 1 | Tim 01 | 34 | 29 | 85.3 | 5 | 1
Sprint 2 | Tim 01 | 72 | 0 | 0 | 0 | 0
Sprint 3 | Tim 01 | 52 | 0 | 0 | 0 | 0
Sprint 4 | Tim 01 | 55 | 0 | 0 | 0 | 0
Sprint 5 | Tim 01 | 55 | 0 | 0 | 0 | 0
Sprint 6 | Tim 01 | 55 | 0 | 0 | 0 | 0
Sprint 1 | Tim 02 | 22 | 9 | 40.9 | 3 | 0
Sprint 2 | Tim 02 | 26 | 0 | 0 | 0 | 0
Sprint 3 | Tim 02 | 20 | 0 | 0 | 0 | 0
Sprint 4 | Tim 02 | 25 | 0 | 0 | 0 | 0
Sprint 5 | Tim 02 | 15 | 0 | 0 | 0 | 0
Sprint 6 | Tim 02 | 16 | 0 | 0 | 0 | 0
Sprint 7 | Tim 02 | 13 | 0 | 0 | 0 | 0
Sprint 1: Persiapan | Tim 03 | 35 | 35 | 100 | 10 | 0
Sprint 2: Persiapan | Tim 03 | 28 | 28 | 100 | 9 | 0
Sprint 3: Login (Integrasi) | Tim 03 | 17 | 17 | 100 | 6 | 0
Sprint 4: Kelola Admin Event | Tim 03 | 46 | 0 | 0 | 0 | 0
Sprint 5: Kelola Event & Input Data Tamu (Generate QR) | Tim 03 | 34 | 0 | 0 | 0 | 0
Sprint 6: CRUD Tamu pada Event yang Di-assign | Tim 03 | 21 | 0 | 0 | 0 | 0
Sprint 7: Scanner QR | Tim 03 | 26 | 0 | 0 | 0 | 0
Sprint 8: Status Kehadiran, Check-in Manual & Export PDF | Tim 03 | 29 | 0 | 0 | 0 | 0
Sprint 9: Kelola Event yang Di-assign (Admin Event) | Tim 03 | 27 | 0 | 0 | 0 | 0
Sprint 10: Dashboard Superadmin | Tim 03 | 21 | 0 | 0 | 0 | 0
Sprint 11: Modifikasi Profile | Tim 03 | 23 | 0 | 0 | 0 | 0
Sprint 12: Pengujian & Revisi (UAT) | Tim 03 | 13 | 0 | 0 | 0 | 0
Sprint 13: Pengujian & Revisi (Bugfix & E2E Final) | Tim 03 | 18 | 0 | 0 | 0 | 0
Sprint 14: Laporan Akhir | Tim 03 | 14 | 0 | 0 | 0 | 0
Sprint 15: Laporan Akhir & Handover | Tim 03 | 12 | 0 | 0 | 0 | 0
Sprint 1 | Tim 04 | 24 | 18 | 75 | 4 | 0
Sprint 2 | Tim 04 | 20 | 0 | 0 | 0 | 0
Sprint 3 | Tim 04 | 27 | 0 | 0 | 0 | 0
Sprint 4 | Tim 04 | 23 | 0 | 0 | 0 | 0
Sprint 5 | Tim 04 | 19 | 0 | 0 | 0 | 0
Sprint 6 | Tim 04 | 16 | 0 | 0 | 0 | 0
Sprint 7 | Tim 04 | 13 | 0 | 0 | 0 | 0
Sprint 1 | Tim 05 | 2 | 2 | 100 | 3 | 2
Sprint 2 | Tim 05 | 58 | 26 | 44.8 | 6 | 9
Sprint 3 | Tim 05 | 51 | 0 | 0 | 1 | 0
Sprint 4 | Tim 05 | 56 | 0 | 0 | 0 | 0
Sprint 5 | Tim 05 | 74 | 0 | 0 | 0 | 0
Sprint 6 | Tim 05 | 68 | 0 | 0 | 0 | 0
Sprint 7 | Tim 05 | 47 | 0 | 0 | 0 | 0
Sprint 8 | Tim 05 | 26 | 0 | 0 | 0 | 0
Sprint 1 | Tim 06 | 0 | 0 | 0 | 3 | 0
Sprint 2 | Tim 06 | 19 | 0 | 0 | 0 | 0
Sprint 3 | Tim 06 | 21 | 0 | 0 | 0 | 0
Sprint 4 | Tim 06 | 19 | 0 | 0 | 0 | 0
Sprint 5 | Tim 06 | 28 | 0 | 0 | 0 | 0
Sprint 1 | Tim 07 | 33 | 7 | 21.2 | 3 | 11
Sprint 2 | Tim 07 | 15 | 0 | 0 | 0 | 0
Sprint 3 | Tim 07 | 35 | 0 | 0 | 0 | 0
Sprint 4 | Tim 07 | 21 | 0 | 0 | 0 | 0
Sprint 5 | Tim 07 | 9 | 0 | 0 | 0 | 0
Sprint 1 | Tim 08 | 0 | 0 | 0 | 5 | 0
Sprint 2 | Tim 08 | 0 | 0 | 0 | 0 | 0
Sprint 3 | Tim 08 | 0 | 0 | 0 | 0 | 0
Sprint 4 | Tim 08 | 0 | 0 | 0 | 0 | 0
Sprint 5 | Tim 08 | 0 | 0 | 0 | 0 | 0
Sprint 6 | Tim 08 | 0 | 0 | 0 | 0 | 0
Sprint 1 | Tim 09 | 13 | 10 | 76.9 | 8 | 8
Sprint 2 | Tim 09 | 34 | 0 | 0 | 0 | 0
Sprint 3 | Tim 09 | 34 | 0 | 0 | 0 | 0
Sprint 4 | Tim 09 | 32 | 0 | 0 | 0 | 0
Sprint 5 | Tim 09 | 40 | 0 | 0 | 0 | 0
Sprint 6 | Tim 09 | 43 | 0 | 0 | 0 | 0

## Monitoring Mingguan
Minggu | Sprint | Tim | Mahasiswa | Task Assigned | Task Done | Task Terlambat | SP Assigned | SP Done | Progress (%) | Commit | Status | Catatan
1 | Sprint 1 | Tim 05 | Ahmad Zaky Ash Shidqi | 3 | 0 | 0 | 2 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
1 | Sprint 1 | Tim 06 | Aditya Fieansyah Putra Pratama | 3 | 3 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 01 | Arini Nur Azizah | 2 | 1 | 0 | 10 | 5 | 50 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 01 | Mufrih Fakhir | 1 | 0 | 0 | 5 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 01 | Muhammad Rengga Putra Kuncoro | 1 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 01 | Rafie Zaidan Umara | 1 | 0 | 0 | 3 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 01 | Zabrina Zerlynda Musanef | 1 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1: Persiapan | Tim 03 | Andi Nur Nabila Syalwani | 3 | 3 | 0 | 12 | 12 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1: Persiapan | Tim 03 | Faith Mary Sani | 2 | 2 | 0 | 7 | 7 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1: Persiapan | Tim 03 | Junathan Richie | 2 | 2 | 0 | 8 | 8 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1: Persiapan | Tim 03 | Kukuh Putra Purwanegara | 3 | 3 | 0 | 8 | 8 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 05 | Ahmad Zaky Ash Shidqi | 3 | 1 | 0 | 2 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 06 | Aditya Fieansyah Putra Pratama | 3 | 3 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 07 | Muhammad Surya Yasar | 5 | 0 | 0 | 11 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 07 | Sinta Probondari Wardani | 2 | 0 | 0 | 6 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 07 | Siti Zahra Ananda Kurniawan | 4 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 07 | adeliarahmaa | 3 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 08 | Akhmad Mustofa Solikin | 3 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 08 | Nabil Jamal Sungkar | 1 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 08 | Tarisha Falah Basuki | 5 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 09 | Achmad Hasan Al Fikri | 5 | 1 | 0 | 6 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 09 | Keisha Syabilla Alia Ghifarani | 7 | 2 | 0 | 7 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
2 | Sprint 1 | Tim 09 | Muhammad Irsyad Habibi | 1 | 1 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 01 | Arini Nur Azizah | 2 | 1 | 0 | 10 | 5 | 50 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 01 | Mufrih Fakhir | 1 | 0 | 0 | 5 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 01 | Muhammad Rengga Putra Kuncoro | 1 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 01 | Rafie Zaidan Umara | 1 | 0 | 0 | 3 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 01 | Zabrina Zerlynda Musanef | 1 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1: Persiapan | Tim 03 | Andi Nur Nabila Syalwani | 3 | 3 | 0 | 12 | 12 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
3 | Sprint 2: Persiapan | Tim 03 | Andi Nur Nabila Syalwani | 1 | 1 | 0 | 3 | 3 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1: Persiapan | Tim 03 | Faith Mary Sani | 2 | 2 | 0 | 7 | 7 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
3 | Sprint 2: Persiapan | Tim 03 | Faith Mary Sani | 3 | 0 | 0 | 9 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1: Persiapan | Tim 03 | Junathan Richie | 2 | 2 | 0 | 8 | 8 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
3 | Sprint 2: Persiapan | Tim 03 | Junathan Richie | 3 | 3 | 0 | 11 | 11 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1: Persiapan | Tim 03 | Kukuh Putra Purwanegara | 3 | 3 | 0 | 8 | 8 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
3 | Sprint 2: Persiapan | Tim 03 | Kukuh Putra Purwanegara | 2 | 0 | 0 | 5 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 05 | Ahmad Zaky Ash Shidqi | 3 | 1 | 2 | 2 | 0 | 0 | 0 | KUNING - Perlu dipantau | (estimasi backfill)
3 | Sprint 2 | Tim 05 | Ahmad Zaky Ash Shidqi | 2 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 2 | Tim 05 | Hamdancml | 1 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 2 | Tim 05 | Mirza Syahrizal Fathir | 2 | 1 | 0 | 13 | 5 | 38.5 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 2 | Tim 05 | Moh. Rafli Gusti Saputra | 8 | 0 | 0 | 32 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 2 | Tim 05 | Muhammad Ikhwan Ma'ruf Santoso | 2 | 0 | 0 | 5 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 06 | Aditya Fieansyah Putra Pratama | 3 | 3 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 07 | Muhammad Surya Yasar | 5 | 0 | 0 | 11 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 07 | Sinta Probondari Wardani | 2 | 0 | 0 | 6 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 07 | Siti Zahra Ananda Kurniawan | 4 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 07 | adeliarahmaa | 3 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 08 | Akhmad Mustofa Solikin | 3 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 08 | Nabil Jamal Sungkar | 1 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 08 | Tarisha Falah Basuki | 5 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 09 | Achmad Hasan Al Fikri | 5 | 1 | 0 | 6 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 09 | Keisha Syabilla Alia Ghifarani | 7 | 3 | 0 | 7 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
3 | Sprint 1 | Tim 09 | Muhammad Irsyad Habibi | 1 | 1 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 01 | Arini Nur Azizah | 2 | 2 | 0 | 10 | 10 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 01 | Arini Nur Azizah | 2 | 0 | 0 | 10 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 01 | Mufrih Fakhir | 1 | 0 | 1 | 5 | 0 | 0 | 0 | MERAH - Tidak aktif | (estimasi backfill)
4 | Sprint 2 | Tim 01 | Mufrih Fakhir | 1 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 01 | Muhammad Rengga Putra Kuncoro | 1 | 1 | 0 | 8 | 8 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 01 | Muhammad Rengga Putra Kuncoro | 4 | 0 | 0 | 23 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 01 | Rafie Zaidan Umara | 1 | 1 | 0 | 3 | 3 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 01 | Rafie Zaidan Umara | 3 | 0 | 0 | 15 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 01 | Zabrina Zerlynda Musanef | 1 | 1 | 0 | 8 | 8 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 01 | Zabrina Zerlynda Musanef | 3 | 0 | 0 | 16 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 02 | Amelia Nova Safitri | 1 | 0 | 0 | 3 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 02 | Haidar Daffa Firzatullah | 1 | 0 | 0 | 5 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 02 | Leyan Harits Rambang Wicaksana | 3 | 2 | 0 | 11 | 6 | 54.5 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 02 | Nona Auliya Wijaya | 1 | 1 | 0 | 3 | 3 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2: Persiapan | Tim 03 | Andi Nur Nabila Syalwani | 1 | 1 | 0 | 3 | 3 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 3: Login (Integrasi) | Tim 03 | Andi Nur Nabila Syalwani | 1 | 1 | 0 | 3 | 3 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2: Persiapan | Tim 03 | Faith Mary Sani | 3 | 3 | 0 | 9 | 9 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 3: Login (Integrasi) | Tim 03 | Faith Mary Sani | 2 | 0 | 0 | 5 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2: Persiapan | Tim 03 | Junathan Richie | 3 | 3 | 0 | 11 | 11 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 3: Login (Integrasi) | Tim 03 | Junathan Richie | 1 | 1 | 0 | 3 | 3 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2: Persiapan | Tim 03 | Kukuh Putra Purwanegara | 2 | 2 | 0 | 5 | 5 | 100 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 3: Login (Integrasi) | Tim 03 | Kukuh Putra Purwanegara | 2 | 1 | 0 | 6 | 3 | 50 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 04 | Bunga Melati Putri Luqman | 2 | 1 | 0 | 8 | 5 | 62.5 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 04 | Haenu Narendra Ramadhani | 2 | 1 | 0 | 7 | 5 | 71.4 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 04 | Nicholas Abel Nathaniel | 1 | 1 | 0 | 3 | 3 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 04 | Nixon Castroman | 2 | 1 | 0 | 6 | 5 | 83.3 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2 | Tim 05 | Ahmad Zaky Ash Shidqi | 2 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2 | Tim 05 | Hamdancml | 1 | 1 | 0 | 8 | 8 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2 | Tim 05 | Mirza Syahrizal Fathir | 2 | 2 | 0 | 13 | 13 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2 | Tim 05 | Moh. Rafli Gusti Saputra | 8 | 0 | 0 | 32 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2 | Tim 05 | Muhammad Ikhwan Ma'ruf Santoso | 2 | 1 | 0 | 5 | 5 | 100 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 06 | Aditya Fieansyah Putra Pratama | 3 | 3 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 07 | Muhammad Surya Yasar | 5 | 0 | 5 | 11 | 0 | 0 | 0 | MERAH - Tidak aktif | (estimasi backfill)
4 | Sprint 1 | Tim 07 | Sinta Probondari Wardani | 2 | 0 | 2 | 6 | 0 | 0 | 0 | MERAH - Tidak aktif | (estimasi backfill)
4 | Sprint 1 | Tim 07 | Siti Zahra Ananda Kurniawan | 4 | 0 | 4 | 8 | 0 | 0 | 0 | MERAH - Tidak aktif | (estimasi backfill)
4 | Sprint 1 | Tim 07 | adeliarahmaa | 3 | 0 | 3 | 8 | 0 | 0 | 0 | MERAH - Tidak aktif | (estimasi backfill)
4 | Sprint 1 | Tim 08 | Akhmad Mustofa Solikin | 3 | 3 | 0 | 0 | 0 | 0 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 08 | Akhmad Mustofa Solikin | 6 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 08 | Nabil Jamal Sungkar | 1 | 1 | 0 | 0 | 0 | 0 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 08 | Nabil Jamal Sungkar | 6 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 08 | Tarisha Falah Basuki | 5 | 5 | 0 | 0 | 0 | 0 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 08 | Tarisha Falah Basuki | 6 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 09 | Achmad Hasan Al Fikri | 5 | 3 | 4 | 6 | 4 | 66.7 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 09 | Achmad Hasan Al Fikri | 2 | 0 | 0 | 3 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 2 | Tim 09 | Ahmad Muqorrobin | 3 | 0 | 0 | 9 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 09 | Keisha Syabilla Alia Ghifarani | 7 | 6 | 4 | 7 | 6 | 85.7 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 09 | Keisha Syabilla Alia Ghifarani | 12 | 0 | 0 | 20 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
4 | Sprint 1 | Tim 09 | Muhammad Irsyad Habibi | 1 | 1 | 0 | 0 | 0 | 0 | 0 | HIJAU - Aktif | (estimasi backfill)
4 | Sprint 2 | Tim 09 | Muhammad Irsyad Habibi | 3 | 0 | 0 | 6 | 0 | 0 | 0 | BIRU - Masih progress | (estimasi backfill)
5 | Sprint 2 | Tim 01 | Arini Nur Azizah | 2 | 0 | 0 | 10 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 01 | Mufrih Fakhir | 1 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 01 | Muhammad Rengga Putra Kuncoro | 4 | 0 | 0 | 23 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 01 | Rafie Zaidan Umara | 3 | 0 | 0 | 15 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 01 | Zabrina Zerlynda Musanef | 3 | 0 | 0 | 16 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 1 | Tim 02 | Amelia Nova Safitri | 1 | 0 | 0 | 3 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 1 | Tim 02 | Haidar Daffa Firzatullah | 1 | 0 | 0 | 5 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 1 | Tim 02 | Leyan Harits Rambang Wicaksana | 3 | 2 | 0 | 11 | 6 | 54.5 | 0 | BIRU - Masih progress
5 | Sprint 1 | Tim 02 | Nona Auliya Wijaya | 1 | 1 | 0 | 3 | 3 | 100 | 0 | BIRU - Masih progress
5 | Sprint 3: Login (Integrasi) | Tim 03 | Andi Nur Nabila Syalwani | 1 | 1 | 0 | 3 | 3 | 100 | 0 | HIJAU - Aktif
5 | Sprint 4: Kelola Admin Event | Tim 03 | Andi Nur Nabila Syalwani | 4 | 0 | 0 | 14 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 3: Login (Integrasi) | Tim 03 | Faith Mary Sani | 2 | 2 | 0 | 5 | 5 | 100 | 0 | HIJAU - Aktif
5 | Sprint 4: Kelola Admin Event | Tim 03 | Faith Mary Sani | 2 | 0 | 0 | 6 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 3: Login (Integrasi) | Tim 03 | Junathan Richie | 1 | 1 | 0 | 3 | 3 | 100 | 0 | HIJAU - Aktif
5 | Sprint 4: Kelola Admin Event | Tim 03 | Junathan Richie | 2 | 0 | 0 | 13 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 3: Login (Integrasi) | Tim 03 | Kukuh Putra Purwanegara | 2 | 2 | 0 | 6 | 6 | 100 | 0 | HIJAU - Aktif
5 | Sprint 4: Kelola Admin Event | Tim 03 | Kukuh Putra Purwanegara | 3 | 0 | 0 | 13 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 1 | Tim 04 | Bunga Melati Putri Luqman | 2 | 1 | 0 | 8 | 5 | 62.5 | 0 | BIRU - Masih progress
5 | Sprint 1 | Tim 04 | Haenu Narendra Ramadhani | 2 | 1 | 0 | 7 | 5 | 71.4 | 0 | BIRU - Masih progress
5 | Sprint 1 | Tim 04 | Nicholas Abel Nathaniel | 1 | 1 | 0 | 3 | 3 | 100 | 0 | BIRU - Masih progress
5 | Sprint 1 | Tim 04 | Nixon Castroman | 2 | 1 | 0 | 6 | 5 | 83.3 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 05 | Ahmad Zaky Ash Shidqi | 2 | 1 | 1 | 0 | 0 | 0 | 0 | HIJAU - Aktif
5 | Sprint 3 | Tim 05 | Ahmad Zaky Ash Shidqi | 1 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 05 | Hamdancml | 1 | 1 | 0 | 8 | 8 | 100 | 0 | HIJAU - Aktif
5 | Sprint 3 | Tim 05 | Hamdancml | 1 | 0 | 0 | 4 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 05 | Mirza Syahrizal Fathir | 2 | 2 | 0 | 13 | 13 | 100 | 0 | HIJAU - Aktif
5 | Sprint 3 | Tim 05 | Mirza Syahrizal Fathir | 4 | 0 | 0 | 18 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 05 | Moh. Rafli Gusti Saputra | 8 | 0 | 8 | 32 | 0 | 0 | 0 | MERAH - Tidak aktif
5 | Sprint 3 | Tim 05 | Moh. Rafli Gusti Saputra | 5 | 0 | 0 | 18 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 05 | Muhammad Ikhwan Ma'ruf Santoso | 2 | 2 | 0 | 5 | 5 | 100 | 0 | HIJAU - Aktif
5 | Sprint 3 | Tim 05 | Muhammad Ikhwan Ma'ruf Santoso | 2 | 0 | 0 | 6 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 1 | Tim 06 | Aditya Fieansyah Putra Pratama | 3 | 3 | 0 | 0 | 0 | 0 | 0 | HIJAU - Aktif
5 | Sprint 2 | Tim 06 | Aditya Fieansyah Putra Pratama | 6 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 06 | Azhar Hafiz Andanianto | 7 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 06 | Dzikrina Hidayani Martin | 5 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 06 | Jasmine Putri Alesyah | 4 | 0 | 0 | 8 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 06 | Rouli Elizabeth Geraldine Aritonang | 4 | 0 | 0 | 3 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 08 | Akhmad Mustofa Solikin | 6 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 08 | Nabil Jamal Sungkar | 6 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 08 | Tarisha Falah Basuki | 6 | 0 | 0 | 0 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 09 | Achmad Hasan Al Fikri | 2 | 0 | 0 | 3 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 09 | Ahmad Muqorrobin | 3 | 0 | 0 | 9 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 09 | Keisha Syabilla Alia Ghifarani | 12 | 0 | 0 | 20 | 0 | 0 | 0 | BIRU - Masih progress
5 | Sprint 2 | Tim 09 | Muhammad Irsyad Habibi | 3 | 0 | 0 | 6 | 0 | 0 | 0 | BIRU - Masih progress